## Sheet1
Sky PO Status & Production LT
460pcs 35W PO-609804 |  | No 5
Material | Supplier | Contact | Email | QPA | On Hand Inventory | Remaining Inventory | Valterra PO Date | SKY PO Date | Material Production Lead Time | Payment From SKY | SKY PO# | SKY PO Qty | Shipping Method | AWB# or B/L# | Material Location | ETA @SKY | SKY Build Date | SKY Ship Date
Cell | Go Power |  |  | 4906 | 114982 | 110076 | 2025-09-18 | Stock
Cable seal, Weather Pack | Go Power |  |  | 943 | 20702 | 19759 |  | Stock
Male Connector | Go Power |  |  | 943 | 16722 | 15779 |  | Stock
Connector Dhelpi | Go Power |  |  | 460 | 9808 | 9348 |  | Stock
TPT 350mm | Zhejiang Zec | John Dong | 15858119899@139.com | 460 | 1236 | 776 |  | Stock
Backsheet WCPC |  |  |  | 86.48 | 311.4 | 224.92 |  | Stock
Backsheet PET |  |  |  | 17.48 | 588 | 570.52 |  | Stock
EVA | First Eva |  |  | 274.4 | 274.4 | 0 |  | Stock
EVA (Front) | Huizhou Baojun | Emma | emma@jsbaojun.cn | 71.5 | 1050 | 978.5 |  | 2026-01-23 | 5-7 Days | 2026-01-26 | PO 008 | 1050 | Air | Done | SKY Warehouse | 2026-02-06 | 2026-02-09
EVA (Back) |  |  |  | 108.2 | 1500 | 1391.8 | [5 empty] | 1500 | Air | Done | SKY Warehouse | 2026-02-06
Solar ribbon | Sunby | Judy Cai | judy@hzdongke.com | 0.74 | 29.44 | 28.7 |  | Stock
Busbar | HZDongke |  |  | 5.06 | 43.42 | 38.36 |  | Stock
Junction Box | China Ruis Industrial | Ben | ben@hongxinxu.com | 460 | 694 | 234 |  | 2025-11-28 | 5-7 Days | 2026-01-14 | PO 090 | 694 | Air | Done | SKY Warehouse | 2026-02-07
Silicone | Local |  |  | 11.5 | 164 | 152.5 |  | Stock
Label Silver | Yihe Industry (Local) |  |  | 460 | 6000 | 5540 |  | Stock
Labels TK 35W | Henan Top Run | Grace | toprungrace@sina.cn | 920 | 8000 | 7080 |  | Stock
High Temp Tape | Mandala Hiba Buana |  |  | 5.52 | 302 | 296.48 |  | 2025-12-08 | Ready Stock |  | PO 200 | 3000 | Local | Local | SKY Warehouse | 2026-02-04
Master Box | Gilang Wijaya (Local) |  |  | 16 | 16 | 0 |  | 2026-01-23 | 7 Days | 2026-01-23 | PO 008 |  | Local | Local | SKY Warehouse | 2026-02-04
1000pcs 50W PO-609684 | - 40 PCS | No 6
Material | Supplier | Contact | Email | QPA | On Hand Inventory | Remaining Inventory | Valterra PO Date | SKY PO Date | Material Production Lead Time | Payment From SKY | SKY PO# | SKY PO Qty | Shipping Method | AWB# or B/L# | Material Location | ETA @SKY | SKY Build Date | SKY Ship Date
Cell | Go Power |  |  | 15000 | 110076 | 95076 | 2025-05-26 | Stock
Cable seal, Weather Pack | Go Power |  |  | 2050 | 19759 | 17709 |  | Stock
Male Connector | Go Power |  |  | 2050 | 15779 | 13729 |  | Stock
Connector Dhelpi | Go Power |  |  | 1000 | 9348 | 8348 |  | Stock
TPT 385mm | Zhejiang Zec | John Dong | 15858119899@139.com | 1000 | 2560 | 1560 |  | 2025-12-12 | 5-7 Days | 2026-01-19 | PO 112 | 2060 | Air | Done | SKY Warehouse | 2026-02-06 | 2026-02-10 | 2026-02-14
Backsheet PET |  |  |  | 118 | 570.52 | 452.52 |  | Stock
EVA (Front) | Huizhou Baojun | Emma | emma@jsbaojun.cn | 703 | 978.5 | 275.5 |  | 2026-01-23 | 5-7 Days | 2026-01-26 | PO 009 | 1050 | Air | Done | SKY Warehouse | 2026-02-06 |  | 40 (11 Mar)
EVA (Back) |  |  |  | 1054.5 | 1391.8 | 337.3 |  |  | 5-7 Days |  | PO 009 | 1500 | Air | Done | SKY Warehouse | 2026-02-06
Solar ribbon | Sunby |  |  | 0.74 | 28.7 | 27.96 |  | Stock
Busbar | HZDongke | Judy Cai | judy@hzdongke.com | 5.06 | 38.36 | 33.3 |  | Stock
Junction Box | China Ruis Industrial | Ben | ben@hongxinxu.com | 1025 | 1264 | 239 |  | 2025-11-28 | 5-7 Days | 2026-01-14 | PO 090 | 1030 | Air | Done | SKY Warehouse | 2026-02-07
Silicone | Local |  |  | 25 | 152.5 | 127.5 |  | Stock
Label Silver | Yihe Industry (Local) |  |  | 1000 | 5000 | 4000 |  | Stock
Label Thermolite 50W | Hennan | Grace |  | 1000 | 2280 | 1280 |  | Stock
Labels TK 50W |  |  |  | 1000 | 2280 | 1280 |  | Stock
High Temp Tape | Mandala Hiba Buana |  |  | 95 | 296.48 | 201.48 |  | 2025-12-08 | Ready Stock |  | PO 200 | 3000 | Local | Local | Supplier Warehouse
Master Box | Gilang Wijaya (Local) |  |  | 34 | 34 | 0 |  | 2026-01-23 | 7 Days | 2026-01-23 | PO 008 |  | Local | Local | Supplier Production
500pcs 35W PO-609820 | Part 1 | No 8
Material | Supplier | Contact | Email | QPA | On Hand Inventory | Remaining Inventory | Valterra PO Date | SKY PO Date | Material Production Lead Time | Payment From SKY | SKY PO# | SKY PO Qty | Shipping Method | AWB# or B/L# | Material Location | ETA @SKY | SKY Build Date | SKY Ship Date
Cell | Go Power |  |  | 5835 | 95076 | 89241 | 2025-10-02 | Stock
Cable seal, Weather Pack | Go Power |  |  | 1025 | 17709 | 16684 |  | Stock
Male Connector | Go Power |  |  | 1025 | 13729 | 12704 |  | Stock
Connector Dhelpi | Go Power |  |  | 500 | 8348 | 7848 |  | Stock | [9 empty] | 500
TPT 350mm | Zhejiang Zec | John Dong | 15858119899@139.com | 500 | 776 | 276 |  | 2026-02-02 | 5-7 Days | 2026-02-03 | PO 010 | 2100 | Air | Confrim with Fedex | Fedex Warehouse China | 2026-02-18 |  | 180 (7 Mar)
Backsheet WCPC 35W |  |  |  | 97.7 | 224.92 | 127.22 | [5 empty] | 660
Backsheet PET |  |  |  | 20 | 452.52 | 432.52 | [5 empty] | 392
EVA (Front) | Huizhou Baojun | Emma | emma@jsbaojun.cn | 197.2 | 275.5 | 78.3 |  | 2026-01-29 | 5-7 Days | 2026-02-03 | PO 017 | 2850 | Sea | Confrim with FTN | Supplier Warehouse | 2026-03-25
EVA (Back) |  |  |  | 295.6 | 337.3 | 41.7 | [5 empty] | 3750 |  |  | Supplier Warehouse
EVA | Sveck/EVA Alternative | Maggie | [5 empty] | 2026-02-09 | 5-7 Days | 2026-02-11 | PO 019 | 2700 | Air | Confrim with Fedex | Supplier Warehouse | 2026-02-19
[12 empty] | 3600 | Sea |  | Supplier Warehouse | 2026-03-10
Solar ribbon | Sunby |  |  | 0.74 | 27.96 | 27.22 |  | Stock
Busbar | HZDongke | Judy Cai | judy@hzdongke.com | 5.06 | 33.3 | 28.24 |  |  | 5-7 Days | 2026-01-19 | PO 111 | 50 | Air | Done | SKY Warehouse | 2026-02-07
Junction Box | China Ruis Industrial | Ben | ben@hongxinxu.com | 500 | 1269 | 769 |  | 2025-11-28 | 5-7 Days | 2026-01-14 | PO 090 | 1030 | Air | Done | SKY Warehouse | 2026-02-07 | 2026-02-14
Silicone | Local |  |  | 11.5 | 127.5 | 116 |  | Stock
Label Silver | Yihe Industry (Local) |  |  | 500 | 4000 | 3500 |  | Stock
Labels TK 35W | Henan |  |  | 1000 | 7080 | 6080 |  | 2026-01-12 | 4 Days | 2026-02-05 | PO 012 | 8000 |  |  | Supplier Warehouse
High Temp Tape | Mandala Hiba Buana |  |  | 5.52 | 296.48 | 290.96 |  | 2025-12-08 | Ready Stock |  | PO 200 | 3000 | Local | Local | Supplier Warehouse
Master Box | Gilang Wijaya (Local) |  |  | 16 | 16 | 0 |  | 2026-01-23 | 7 Days | 2026-01-23 | PO 008 |  | Local | Local
1000pcs 50W PO-609784 |  | No 7
Material | Supplier | Contact | Email | QPA | On Hand Inventory | Remaining Inventory | Valterra PO Date | SKY PO Date | Material Production Lead Time | Payment Date | SKY PO# | SKY PO Qty | Shipping Method | AWB# or B/L# | Material Location | ETA @SKY | SKY Build Date | SKY Ship Date
Cell | Go Power |  |  | 15000 | 95076 | 80076 | 2025-09-02 | Stock
Cable seal, Weather Pack | Go Power |  |  | 2050 | 16684 | 14634 |  | Stock
Male Connector | Go Power |  |  | 2050 | 12704 | 10654 |  | Stock
Connector Dhelpi | Go Power |  |  | 1000 | 7848 | 6848 |  | Stock
TPT 385mm | Zhejiang Zec | John Dong | 15858119899@139.com | 1000 | 1560 | 560 |  | 2026-02-02 | 5-7 Days | 2026-02-03 | PO 010 | 2100 | Air | Confrim with Fedex | Fedex Warehouse China | 2026-02-18
Backsheet PET |  |  |  | 118 | 432.52 | 314.52 | [5 empty] | 392
EVA (Front) | Huizhou Baojun | Emma | emma@jsbaojun.cn |  | 78.3 | 78.3 |  | 2026-01-29 | 5-7 Days | 2026-02-03 | PO 017 | 2850 | Sea | Confrim with FTN | Supplier Warehouse | 2026-03-10 | 2026-03-10 | 140 (11 Mar)
EVA (Back) |  |  |  |  | 41.7 | 41.7 | [5 empty] | 3750 |  |  | Supplier Warehouse |  |  | 360 (17 Mar)
EVA | Sveck/EVA Alternative | Maggie |  | 1757.5 | 1222.8 | -534.7 |  | 2026-02-09 | 5-7 Days | 2026-02-11 | PO 019 | 2700 | Air | Confrim with Fedex | Supplier Warehouse | 2026-03-05 |  | 500 (27 (Mar)
[12 empty] | 3600 | Sea |  | Supplier Warehouse | 2026-03-25
Solar ribbon | Sunby |  |  | 0.74 | 27.22 | 26.48 |  | Stock
Busbar | HZDongke | Judy Cai | judy@hzdongke.com | 5.06 | 78.24 | 73.18 |  |  | 5-7 Days | 2026-01-19 | PO 111 | 50 | Air | Done | SKY Warehouse | 2026-02-07
Junction Box | China Ruis Industrial | Ben | ben@hongxinxu.com | 1025 | 769 | -256 |  | 2026-02-02 | 5-7 Days | 2026-03-06 | PO 013 | 3240 | Air & Sea | Confrim with Fedex | Supplier Production | 2026-03-13
Silicone | Local |  |  | 25 | 116 | 91 |  | Stock
Label Silver | Yihe Industry (Local) |  |  | 1000 | 3500 | 2500 |  | Stock
Label Thermolite 50W | Hennan | Grace |  | 1000 | 1280 | 280 |  | 2026-01-12 | 4 Days | 2026-02-05 | PO 012 | 5250 | DHL |  | Supplier Warehouse
Labels TK 50W |  |  |  | 1000 | 1280 | 280 |  |  |  |  | PO 012 | 5250 | DHL |  | Supplier Warehouse
High Temp Tape | Mandala Hiba Buana |  |  | 95 | 290.96 | 195.96 |  | 2025-12-08 | Ready Stock |  | PO 200 | 3000 | Local | Local | Supplier Warehouse
Master Box | Gilang Wijaya (Local) |  |  | 34 | 0 | -34 |  | 2026-01-23 | 7 Days | 2026-01-23 | PO 008 | 68 | Local | Local | Supplier Production | FU to Adhel
1500pcs 35W PO-609820 | Part 2 | No 8
Material | Supplier | Contact | Email | QPA | On Hand Inventory | Remaining Inventory | Valterra PO Date | SKY PO Date | Material Production Lead Time | Payment Date | SKY PO# | SKY PO Qty | Shipping Method | AWB# or B/L# | Material Location | ETA @SKY | SKY Build Date | SKY Ship Date
Cell | Go Power |  |  | 15499 | 80076 | 64577 | 2025-10-02 | Stock
Cable seal, Weather Pack | Go Power |  |  | 3075 | 14634 | 11559 |  | Stock
Male Connector | Go Power |  |  | 3075 | 10654 | 7579 |  | Stock
Connector Dhelpi | Go Power |  |  | 1500 | 6848 | 5348 |  | Stock
TPT 350mm | Zhejiang Zec | John Dong | 15858119899@139.com | 1500 | 2376 | 876 |  | 2026-02-02 | 5 - 7 Dats | 2026-02-03 | PO 010 | 2100 | Air | Confirm with Fedex | SKY Warehouse | 2026-02-18
Backsheet WCPC |  |  |  | 278.3 | 787.22 | 508.92 | [5 empty] | 660
Backsheet PET |  |  |  | 56 | 706.52 | 650.52 | [5 empty] | 392
EVA (Front) | Huizhou Baojun | Emma | emma@jsbaojun.cn | 0 | 78.3 | 78.3 |  | 2026-01-29 | 5-7 Days | 2026-02-03 | PO 017 | 2850 | Sea | Confrim with FTN | Supplier Warehouse | 2026-03-25 | 2026-03-06 | 540 - (11 Mar)
EVA (Back) |  |  |  | 0 | 41.7 | 41.7 | [5 empty] | 3750 |  |  | Supplier Warehouse
EVA | Sveck/EVA Alternative | Maggie |  | 1477.2 | 2700 | 1222.8 |  | 2026-02-09 | 5-7 Days | 2026-02-11 | PO 019 | 2700 | Air | Confrim with Fedex | Supplier Warehouse | 2026-03-05 |  | 900 (16 Mar) |  | 3560
[12 empty] | 3600 | Sea |  | Supplier Warehouse | 2026-03-25
Solar ribbon | Sunby |  |  | 2.46 | 26.48 | 24.02 |  | Stock | [9 empty] | 540 (27 Mar)
Busbar | HZDongke | Judy Cai | judy@hzdongke.com | 16.94 | 73.18 | 56.24 |  |  | 5-7 Days | 2026-01-19 | PO 111 | 50 | Air | Done | SKY Warehouse | 2026-02-07
Junction Box | China Ruis Industrial | Ben | ben@hongxinxu.com | 1550 | -256 | -1806 |  | 2026-02-02 | 5-7 Days | 2026-03-06 | PO 013 | 1500 | Air | Done | SKY Warehouse | 2026-03-13 | 0 | 720 (03 Apr)
[12 empty] | 1740 | Air | Confirm with Fedex | Supplier Warehouse | 2026-03-25
Silicone | Local |  |  | 38.5 | 136 | 97.5 |  | Stock
Label Silver | Yihe Industry (Local) |  |  | 1500 | 2500 | 1000 |  | Stock | [9 empty] | 800 (9 Apr)
Labels TK 35W | Henan |  |  | 3000 | 6080 | 3080 |  | 2026-01-12 | 4 Days | 2026-02-05 | PO 012 | 8000 |  |  | Supplier Warehouse
High Temp Tape | Mandala Hiba Buana |  |  | 89.48 | 195.96 | 106.48 |  | 2025-12-08 | Ready Stock |  | PO 200 | 3000 | Local | Local | Supplier Warehouse
Master Box | Gilang Wijaya (Local) |  |  | 50 | 0 | -50 |  | 2026-01-23 | 7 Days | 2026-03-06 | PO 008 | 70 | Local | Local |  | FU to Adhel
1000pcs 50W PO-609880 |  | No 9
Material | Supplier | Contact | Email | QPA | On Hand Inventory | Remaining Inventory | Valterra PO Date | SKY PO Date | Material Production Lead Time | Payment Date | SKY PO# | SKY PO Qty | Shipping Method | AWB# or B/L# | Material Location | ETA @SKY | SKY Build Date | SKY Ship Date
Cell | Go Power |  |  | 15000 | 64577 | 49577 | 2025-11-18 | Stock
Cable seal, Weather Pack | Go Power |  |  | 2050 | 11559 | 9509 |  | Stock
Male Connector | Go Power |  |  | 2050 | 7579 | 5529 |  | Stock
Connector Dhelpi | Go Power |  |  | 1000 | 5348 | 4348 |  | Stock
TPT 385mm | Zhejiang Zec | John Dong | 15858119899@139.com | 1000 | 560 | -440 |  | 2026-03-06 | 5-7 Days | 2026-03-06 | PO.023 | 1030 | Sea |  |  | 2026-03-25
Backsheet PET |  |  |  | 118 | 650.52 | 532.52 |  | Stock
EVA (Front) | Huizhou Baojun | Emma | emma@jsbaojun.cn | 703 | 78.3 | -624.7 |  | 2026-01-29 | 5-7 Days | 2026-02-03 | PO 017 | 2850 | Sea | Confrim with FTN | On The Way | 2026-03-25 | 2026-04-07 | 1000 (11 Apr)
EVA (Back) |  |  |  | 1054.5 | 41.7 | -1012.8 | [5 empty] | 3750 |  |  | On The Way
EVA | Sveck/EVA Alternative | Maggie |  | 1757.5 |  |  |  | 2026-02-09 | 5-7 Days | 2026-02-11 | PO 019 | 2250 | Air | Confrim with Fedex | Port JKT | 2026-03-17
[12 empty] | 4050 | Sea |  | Port JKT
Solar ribbon | Sunby |  |  | 2 | 24.02 | 22.02 |  | Stock
Busbar | HZDongke | Judy Cai | judy@hzdongke.com | 25 | 56.24 | 31.24 |  |  | 5-7 Days | 2026-01-19 | PO 111 | 50 | Air | Done | SKY Warehouse | 2026-02-07
Junction Box | China Ruis Industrial | Ben | ben@hongxinxu.com | 1025 | -1806 | -2831 |  | 2026-02-02 | 5-7 Days | 2026-03-06 | PO 013 | 3240 | Air | Confrim with Fedex | Supplier Production | 2026-03-25
Silicone | Local |  |  | 25 | 97.5 | 72.5 |  | Stock
Label Thermolite 50W | Henan | Grace |  | 1000 | 280 | -720 |  | 2026-01-12 | 4 Days | 2026-02-05 | PO 012 | 5250 | Air by DHL |  | DHL Warehouse | 2026-03-16
Labels TK 50W |  |  |  | 1000 | 280 | -720 |  |  | 4 Days |  | PO 012 | 5250 | Air by DHL |  | DHL Warehouse | 2026-03-16
High Temp Tape | Mandala Hiba Buana |  |  | 95 | 106.48 | 11.48 |  | 2025-12-08 | Ready Stock |  | PO 200 | 3000 | Local | Local | Supplier Warehouse
Master Box | Gilang Wijaya (Local) |  |  | 34 | 0 | -34 |  | 2026-01-23 | 7 Days | 2026-03-06 | PO 008 |  | Local | Local | Production by Supplier | FU to Adhel
2000pcs 35W PO-609820 | Part 3 | No 8
Material | Supplier | Contact | Email | QPA | On Hand Inventory | Remaining Inventory | Valterra PO Date | SKY PO Date | Material Production Lead Time | Payment Date | SKY PO# | SKY PO Qty | Shipping Method | AWB# or B/L# | Material Location | ETA @SKY | SKY Build Date | SKY Ship Date
Cell | Go Power |  |  | 21334 | 49577 | 28243 | 2025-10-02 | Stock
Cable seal, Weather Pack | Go Power |  |  | 4100 | 9509 | 5409 |  | Stock
Male Connector | Go Power |  |  | 4100 | 5529 | 1429 |  | Stock
Connector Dhelpi | Go Power |  |  | 2000 | 4348 | 2348 |  | Stock
TPT 350mm | Zhejiang Zec | John Dong | 15858119899@139.com | 2000 | 2976 | 976 |  | 2026-03-06 | 5-7 Days | 2026-03-06 | PO 023 | 2100 | Sea |  |  | 2026-03-25 | 2026-03-06 | 540 - 11 Mar | Done
Backsheet WCPC |  |  |  | 390.5 | 508.92 | 118.42 |  | 2026-03-06 | 5-7 Days | 2026-03-06 |  | 880 | Sea |  |  | 2026-03-25
Backsheet PET |  |  |  | 76 | 532.52 | 456.52 |  | Stock | [9 empty] | 900 (16 Mar) | 2026-03-17
EVA (Front) | Huizhou Baojun | Emma | emma@jsbaojun.cn | 788 | -624.7 | -1412.7 |  | 2026-01-29 | 5-7 Days | 2026-02-03 | PO 017 | 2850 | Sea | Confrim with FTN | On the Way (Sea) | 2026-03-25
EVA (Back) |  |  |  | 1182 | -1012.8 | -2194.8 | [5 empty] | 3750 |  |  | On the Way (Sea) |  |  | 540 (27 Mar) | po.013
EVA | Sveck/EVA Alternative | Maggie |  | 1970 |  |  |  | 2026-02-09 | 5-7 Days | 2026-02-11 | PO 019 | 2250 | Air | Confrim with Fedex | Port JKT | 2026-03-17
[12 empty] | 4050 | Sea |  | Port JKT |  |  | 720 (03 Apr)
Solar ribbon | Sunby | Local |  | 3.2 | 22.02 | 18.82 |  | Stock
Busbar | HZDongke | Judy Cai | judy@hzdongke.com | 22 | 31.24 | 9.24 |  |  | 5-7 Days | 2026-01-19 | PO 111 | 50 | Air | Done | SKY Warehouse | 2026-02-07 |  | 800 (9 Apr)
Junction Box | China Ruis Industrial | Ben | ben@hongxinxu.com | 2050 | -741 | -2791 |  | 2026-03-06 | 5-7 Days | 2026-03-10 | PO 020 | 2090 | Sea |  | Production by Supplier | 2026-04-01 |  |  | 2090 Pcs
Silicone | Local |  |  | 50 | 72.5 | 22.5 |  | Stock
Label Silver | Yihe Industry (Local) |  |  | 2000 | 3000 | 1000 |  | Stock
Labels TK 35W | Henan |  |  | 4000 | 3080 | -920 |  | 2026-01-12 | 4 Days | 2026-02-05 | PO 009 |  |  |  |  | FU to Adhel
High Temp Tape | Mandala Hiba Buana |  |  | 95 | 11.48 | -83.52 |  | 2025-12-08 | Ready Stock |  | PO 200 |  | Local | Local
Master Box | Gilang Wijaya (Local) |  |  | 67 | 0 | -67 |  | 2026-03-10 | 5 Days | 2026-03-13 | PO 010 |  | Local | Local
1000pcs 50W PO-609900 |  | No 10
Material | Supplier | Contact | Email | QPA | On Hand Inventory | Remaining Inventory | Valterra PO Date | SKY PO Date | Material Production Lead Time | Payment Date | SKY PO# | SKY PO Qty | Shipping Method | AWB# or B/L# | Material Location | ETA @SKY | SKY Build Date | SKY Ship Date
Cell | Go Power |  |  | 15000 | 28243 | 13243 | 2025-11-21 | Stock
Cable seal, Weather Pack | Go Power |  |  | 2050 | 5409 | 3359 |  | Stock
Male Connector | Go Power |  |  | 2050 | 1429 | -621 |  | 2026-03-13 | by Go Power | Need Payback | PO.031 | 8500 | Air | [5 empty] | 714.5
Connector Dhelpi | Go Power |  |  | 1000 | 2348 | 1348 |  | Stock
TPT 385mm | Zhejiang Zec | John Dong | 15858119899@139.com | 1000 | -440 | -1440 |  | 2026-03-06 | 5-7 Days | 2026-03-06 | PO 023
Backsheet PET |  |  |  | 118 | 532.52 | 414.52 |  | 2026-03-06 | 5-7 Days | 2026-03-06
Backsheet WCPC 380mm |  |  |  | 355.3 | 304 | -51.3 |  | 2026-03-06 | 5-7 Days | 2026-03-10 | Rev 030
EVA (Front) | Huizhou Baojun | Emma | emma@jsbaojun.cn | 703 | -1412.7 | -2115.7 |  | 2026-01-29 | 5-7 Days | 2026-02-03 | PO 017 | 2850 | Sea | Confrim with FTN | Supplier Warehouse | 2026-03-25 | 2026-04-13 | 1000 (17 Apr)
EVA (Back) |  |  |  | 1054.5 | -2194.8 | -3249.3 | [5 empty] | 3750 |  |  | Supplier Warehouse
EVA (Front) | Sveck/EVA Alternative | Maggie |  | 1757.5 |  |  |  | 2026-02-09 | 5-7 Days | 2026-02-11 | PO 019 | 2250 | Air | Confrim with Fedex | Supplier Warehouse | 2026-03-05
EVA (Back) | [11 empty] | 4050 | Sea |  | Supplier Warehouse | 2026-03-25
Solar ribbon | Shanghai Fenxiang |  |  | 2 | 18.82 | 16.82 |  | 2026-03-06 | 15 Days | 2026-03-10 | PO.026 | 40 | Sea
Busbar |  |  |  | 25 | 9.24 | -15.76 |  | 2026-03-06 | 15 Days | 2026-03-10 | PO.026 | 281 | Sea
Junction Box | China Ruis Industrial | Ben | ben@hongxinxu.com | 1025 | -2791 | -3816 |  | 2026-03-06 | 5-7 Days | 2026-03-27 | PO 024 |  |  |  |  | 2026-04-08
Silicone |  |  |  | 25 | 22.5 | -2.5 |  | 2026-03-16 | 3 Days | 2026-03-26 | Open New PO
Label Thermolite 50W | Henan | Grace |  | 1000 | 1000 | 0 |  | 2026-03-06 | 5-7 Days | 2026-03-10 | PO 025 | 2100 |  |  |  | FU to Adhel
Labels TK 50W |  |  |  | 1000 | -720 | -1720 |  | 2026-03-06 | 5-7 Days | 2026-03-10 | PO 025 |  |  |  |  | FU to Adhel
High Temp Tape | Mandala Hiba Buana |  |  | 95 | -83.52 | -178.52 |  | 2026-03-26 | 3 Days | 2026-03-31 | Open New PO
Master Box | Gilang Wijaya (Local) |  |  | 34 | -34 | -68 |  | 2026-03-26 | 3 Days | 2026-03-31 | Open New PO
2000pcs 35W PO-609915 |  | No 11
Material | Supplier | Contact | Email | QPA | On Hand Inventory | Remaining Inventory | Valterra PO Date | SKY PO Date | Material Production Lead Time | Payment Date | SKY PO# | SKY PO Qty | Shipping Method | AWB# or B/L# | Material Location | ETA @SKY | SKY Build Date | SKY Ship Date
Cell | Go Power |  |  | 21334 | 13243 | -8091 | 2025-12-02 | 2026-03-13 | by Go Power | Need Payback | PO.031 | 100000 | Sea
Cable seal, Weather Pack | Go Power |  |  | 4100 | 3359 | -741 |  | 2026-03-13 | by Go Power | Need Payback | PO.031 | 5000 | Air
Male Connector | Go Power |  |  | 4100 | -621 | -4721 |  | 2026-03-13 | by Go Power | Need Payback | PO.031 | 8500 | Air
Connector Dhelpi | Go Power |  |  | 2000 | 1348 | -652 |  | 2026-03-13 | by Go Power | Need Payback | PO.031 | 3000 | Air
TPT 350mm | Zhejiang Zec | John Dong | 15858119899@139.com | 2000 | 976 | -1024 |  | 2026-03-06 | 5-7 Days | 2026-03-11 | REV PO 030 | 2100 | Air
[12 empty] | 2100 | Sea
Backsheet WCPC |  |  |  | 86.48 | 118.42 | 31.94 | [5 empty] | 880 | Sea
Backsheet PET |  |  |  | 76 | 414.52 | 338.52 | [5 empty] | 392 | Sea
EVA (First EVA) | First EVA |  |  | 2025.75 | 0 | -2025.75 |  | 2026-01-29 | 5-7 Days | Need BP 50% (13 Mar 2025) | PO.011 | 6858 | Sea
EVA (Front) | Huizhou Baojun | Emma | emma@jsbaojun.cn | 0 |  |  |  | 2026-01-29 | 5-7 Days | 2026-02-03 | PO 017 | 2850 | Sea | Confrim with FTN | Supplier Warehouse | 2026-03-25 | 2026-04-17 | 2000 (25 Apr)
EVA (Back) |  |  |  | 0 | [7 empty] | 3750 |  |  | Supplier Warehouse
EVA | Sveck/EVA Alternative | Maggie |  | 0 |  |  |  | 2026-02-09 | 5-7 Days | 2026-02-11 | PO 019 | 2250 | Air | Confrim with Fedex | Supplier Warehouse | 2026-03-05
[12 empty] | 4050 | Sea |  | Supplier Warehouse | 2026-03-25
Solar ribbon | Shanghai Fenxiang |  |  | 3.2 | 16.82 | 13.62 |  | 2026-03-06 | 5-7 Days | 2026-03-10 | PO.026 | 40 | Sea
Busbar |  |  |  | 22 | -15.76 | -37.76 |  | 2026-03-06 | 5-7 Days | 2026-03-10 | PO.026 | 281 | Sea
Junction Box | China Ruis Industrial | Ben | ben@hongxinxu.com | 2050 | -3816 | -5866 |  | 2026-03-06 | 5-7 Days | 2026-03-31 | PO.025 | 4120
Silicone |  |  |  | 50 | -2.5 | -52.5 |  | 2026-04-03 | 3 Days | 2026-04-07 | Open New PO
Label Silver | Yihe Industry (Local) |  |  | 2000 | 1000 | -1000 |  | 2026-04-03 | 3 Days | 2026-04-07 | Open New PO
Labels TK 35W | Henan |  |  | 4000 | -920 | -4920 |  | 2026-01-12 | 4 Days | 2026-02-05 | PO 012 | 8000 |  |  | Supplier Warehouse | FU to Adhel
High Temp Tape | Mandala Hiba Buana |  |  | 95 | -178.52 | -273.52 |  | 2026-04-03 | 3 Days | 2026-04-07 | Open New PO
Master Box | Gilang Wijaya (Local) |  |  | 67 | 0 | -67 |  | 2026-04-03 | 3 Days | 2026-04-07 | Open New PO
5pcs 30W 3-diode PO-609915 |  | No 11
Material | Supplier | Contact | Email | QPA | On Hand Inventory | Remaining Inventory | Valterra PO Date | SKY PO Date | Material Production Lead Time | Payment Date | SKY PO# | SKY PO Qty | Shipping Method | AWB# or B/L# | Material Location | ETA @SKY | SKY Build Date | SKY Ship Date
Cell | Go Power |  |  | 0 | -8091 | -8091 | 2025-12-02 | 2026-03-13 | by Go Power | Need Payback | PO.031 | 100000 | Sea
Cable seal, Weather Pack | Go Power |  |  | 0 | -741 | -741 |  | 2026-03-13 | by Go Power | Need Payback | PO.031 | 5000 | Air
Male Connector | Go Power |  |  | 0 | -4721 | -4721 |  | 2026-03-13 | by Go Power | Need Payback | PO.031 | 8500 | Air
Connector Dhelpi | Go Power |  |  | 0 | -652 | -652 |  | 2026-03-13 | by Go Power | Need Payback | PO.031 | 3000 | Air
TPT 350mm | Zhejiang Zec | John Dong | 15858119899@139.com | 0 | -1024 | -1024 |  | 2026-03-06 | 5-7 Days |  | Open New PO |  | Sea
Backsheet WCPC |  |  |  | 0 | 31.94 | 31.94 |  | Stock
Backsheet PET |  |  |  | 0 | 338.52 | 338.52 |  | Stock
EVA (First EVA) | First EVA |  |  | 0 | 0 | 0 |  | 2026-01-29 | 5-7 Days | Need BP 50% (13 Mar 2025) | PO.011 | 6858 | Sea
EVA (Front) | Huizhou Baojun | Emma | emma@jsbaojun.cn | 0 |  |  |  | 2026-01-29 | 5-7 Days | 2026-02-03 | PO 017 | 2850 | Sea | Confrim with FTN | Supplier Warehouse | 2026-03-25 | 2026-03-03 | 2026-03-04
EVA (Back) |  |  |  | 0 | [7 empty] | 3750 |  |  | Supplier Warehouse
EVA | Sveck/EVA Alternative | Maggie |  | 0 |  |  |  | 2026-02-09 | 5-7 Days | 2026-02-11 | PO 019 | 2250 | Air | Confrim with Fedex | Supplier Warehouse | 2026-03-05
[12 empty] | 4050 | Sea |  | Supplier Warehouse | 2026-03-25
Solar ribbon | Shanghai Fenxiang |  |  | 0 | 13.62 | 13.62 |  | 2026-03-06 | 5-7 Days | 2026-03-10 | PO.026 | 40 | Sea
Busbar |  |  |  | 0 | -37.76 | -37.76 |  | 2026-03-06 | 5-7 Days | 2026-03-10 | PO.026 | 281 | Sea
Junction Box 3 Diode | China Ruis Industrial | Ben | ben@hongxinxu.com | 0 |  | 0 |  | Waiting Sample Arrived
Silicone |  |  |  | 0 | -52.5 | -52.5 |  | Stock
Label Silver | Yihe Industry (Local) |  |  | 0 | -1000 | -1000 |  | Stock
Label Thermolite 40W | Henan |  |  | 0 | 2000 | 2000 |  | Stock
Labels TK 35W |  |  |  | 0 | -4920 | -4920 |  | Stock
High Temp Tape | Mandala Hiba Buana |  |  | 0 | -273.52 | -273.52 |  | Stock
Master Box | Gilang Wijaya (Local) |  |  | 0 |  | 0 |  | Packaging will be Custom by Engineering
material
2000pcs 50W PO-609926 |  | No 12
Material | Supplier | Contact | Email | QPA | On Hand Inventory | Remaining Inventory | Valterra PO Date | SKY PO Date | Material Production Lead Time | Payment Date | SKY PO# | SKY PO Qty | Shipping Method | AWB# or B/L# | Material Location | ETA @SKY | SKY Build Date | SKY Ship Date
Cell | Go Power |  |  | 30000 | -8091 | -38091 | 2025-12-09 | 2026-03-13 | by Go Power | Need Payback | PO.031 | 100000 | Sea
Cable seal, Weather Pack | Go Power |  |  | 4100 | -741 | -4841 |  | 2026-03-13 | by Go Power | Need Payback | PO.031 | 5000 | Air
Male Connector | Go Power |  |  | 4100 | -4721 | -8821 |  | 2026-03-13 | by Go Power | Need Payback | PO.031 | 8500 | Air
Connector Dhelpi | Go Power |  |  | 2000 | -652 | -2652 |  | 2026-03-13 | by Go Power | Need Payback | PO.031 | 3000 | Air
TPT 385mm | Zhejiang Zec | John Dong | 15858119899@139.com | 2000 | -1440 | -3440 |  | 2026-03-06 | 5-7 Days | 2026-03-31 | PO 027 |  | Sea
Backsheet PET |  |  |  | 236 | 338.52 | 102.52 |  | 2026-03-06 | 5-7 Days | 2026-03-31 | PO 027 |  | Sea
Backsheet WCPC 380mm |  |  |  | 710.6 | -51.3 | -761.9 |  | 2026-03-06 | 5-7 Days | 2026-03-31 | PO 027
EVA (First EVA) | First EVA |  |  | 2025.75 | 0 | -2025.75 |  | 2026-01-29 | 5-7 Days | Need BP 50% (13 Mar 2025) | PO.011 | 6858 | Sea
EVA (Front) | Huizhou Baojun | Emma | emma@jsbaojun.cn | 1406 | 0 | -1406 |  | 2026-01-29 | 5-7 Days | 2026-02-03 | PO 017 | 2850 | Sea | Confrim with FTN | Supplier Warehouse | 2026-03-25 | 2026-04-27 | 720 (2 May)
EVA (Back) |  |  |  | 2109 | 0 | -2109 | [5 empty] | 3750 |  |  | Supplier Warehouse
EVA (Front) | Sveck/EVA Alternative | Maggie |  | 3515 |  |  |  | 2026-02-09 | 5-7 Days | 2026-02-11 | PO 019 | 2250 | Air | Confrim with Fedex | Supplier Warehouse | 2026-03-05 |  | 1280 (8 May)
EVA (Back) | [11 empty] | 4050 | Sea |  | Supplier Warehouse | 2026-03-25
Solar ribbon | Shanghai Fenxiang |  |  | 4 | 13.62 | 9.62 |  | 2026-03-06 | 5-7 Days | 2026-03-10 | PO.026 | 40 | Sea
Busbar |  |  |  | 50 | -37.76 | -87.76 |  | 2026-03-06 | 5-7 Days | 2026-03-10 | PO.026 | 281 | Sea
Junction Box | China Ruis Industrial | Ben | ben@hongxinxu.com | 2050 | -5866 | -7916 |  | 2026-03-26 | 5-7 Days | 2026-03-31 | PO.028 | 3190
Silicone |  |  |  | 50 | -52.5 | -102.5 |  | 2026-03-31 | 5-7 Days | 2026-04-07 | Open New PO
Label Thermolite 50W | Henan | Grace |  | 2000 | 0 | -2000 |  | 2026-03-26 | 5-7 Days | 2026-03-31 | Open New PO
Labels TK 50W |  |  |  | 2000 | -1720 | -3720 |  | 2026-03-26 | 5-7 Days | 2026-03-31 | Open New PO
High Temp Tape | Mandala Hiba Buana |  |  | 190 | -273.52 | -463.52 |  | 2026-03-31 | 5-7 Days | 2026-04-07 | Open New PO
Master Box | Gilang Wijaya (Local) |  |  | 67 |  | -67 |  | 2026-03-31 | 5-7 Days | 2026-04-07 | Open New PO
1000pcs 50W PO-609945 |  | No 13
Material | Supplier | Contact | Email | QPA | On Hand Inventory | Remaining Inventory | Valterra PO Date | SKY PO Date | Material Production Lead Time | Payment Date | SKY PO# | SKY PO Qty | Shipping Method | AWB# or B/L# | Material Location | ETA @SKY | SKY Build Date | SKY Ship Date
Cell | Go Power |  |  | 15000 | -38091 | -53091 | 2025-12-19 | 2026-03-13 | by Go Power | Need Payback | PO.031 | 100000 | Sea
Cable seal, Weather Pack | Go Power |  |  | 2050 | -741 | -2791 |  | 2026-03-13 | by Go Power | Need Payback | PO.031 | 5000 | Air
Male Connector | Go Power |  |  | 2050 | -8821 | -10871 |  | 2026-03-13 | by Go Power | Need Payback | PO.031 | 8500 | Air
Connector Dhelpi | Go Power |  |  | 1000 | -652 | -1652 |  | 2026-03-13 | by Go Power | Need Payback | PO.031 | 3000 | Air
TPT 385mm | Zhejiang Zec | John Dong | 15858119899@139.com | 1000 | -3440 | -4440 |  | 2026-03-06 | 5-7 Days | 2026-03-13 | PO 027 |  | Sea
Backsheet PET |  |  |  | 118 | 102.52 | -15.48 |  | 2026-03-06 | 5-7 Days | 2026-03-13 | PO 027 |  | Sea
Backsheet WCPC 380mm |  |  |  | 355.3 | -761.9 | -1117.2 |  | 2026-03-06 | 5-7 Days | 2026-03-13 | PO 027
EVA (First EVA) | First EVA |  |  | 2025.75 | 0 | -2025.75 |  | 2026-01-29 | 5-7 Days | Need BP 50% (13 Mar 2025) | PO.011 | 6858 | Sea
EVA (Front) | Huizhou Baojun | Emma | emma@jsbaojun.cn | 703 | -1406 | -2109 |  | 2026-01-29 | 5-7 Days | 2026-02-03 | PO 017 | 2850 | Sea | Confrim with FTN | Supplier Warehouse | 2026-03-25 | 2026-05-06 | 1000 (12 May)
EVA (Back) |  |  |  | 1054.5 | -2109 | -3163.5 | [5 empty] | 3750 |  |  | Supplier Warehouse
EVA (Front) | Sveck/EVA Alternative | Maggie |  | 1757.5 |  |  |  | 2026-02-09 | 5-7 Days | 2026-02-11 | PO 019 | 2250 | Air | Confrim with Fedex | Supplier Warehouse | 2026-03-05
EVA (Back) | [11 empty] | 4050 | Sea |  | Supplier Warehouse | 2026-03-25
Solar ribbon | Shanghai Fenxiang |  |  | 2 | 9.62 | 7.62 |  | 2026-03-06 | 5-7 Days | 2026-03-10 | PO.026 | 40 | Sea
Busbar |  |  |  | 25 | -87.76 | -112.76 |  | 2026-03-06 | 5-7 Days | 2026-03-10 | PO.026 | 281 | Sea
Junction Box | China Ruis Industrial | Ben | ben@hongxinxu.com | 1025 | -7916 | -8941 |  | 2026-03-26 | 5-7 Days | 2026-03-31 | PO.028 | 3190
Silicone |  |  |  | 25 | -102.5 | -127.5 |  | 2026-03-31 | 5-7 Days | 2026-04-07 | Open New PO
Label Thermolite 50W | Henan | Grace |  | 1000 | -2000 | -3000 |  | 2026-03-26 | 5-7 Days | 2026-03-31 | Open New PO
Labels TK 50W |  |  |  | 1000 | -3720 | -4720 |  | 2026-03-26 | 5-7 Days | 2026-03-31 | Open New PO
High Temp Tape | Mandala Hiba Buana |  |  | 95 | -463.52 | -558.52 |  | 2026-03-31 | 5-7 Days | 2026-04-07 | Open New PO
Master Box | Gilang Wijaya (Local) |  |  | 34 |  | -34 |  | 2026-03-31 | 5-7 Days | 2026-04-07 | Open New PO
1500pcs110W PO-609614 |  | No 4
Material | Supplier | Contact | Email | QPA | On Hand Inventory | Remaining Inventory | Valterra PO Date | SKY PO Date | Material Production Lead Time | Payment Date | SKY PO# | SKY PO Qty | Shipping Method | AWB# or B/L# | Material Location | ETA @SKY | SKY Build Date | SKY Ship Date
Cell | Go Power |  |  | 48000 | -53091 | -101091 | 2025-03-28 | TBD |  |  | Open New PO | 100000 | Sea
TPT 110W (570*1165mm) | Zhejiang Zec | John Dong | 15858119899@139.com | 1500 | 0 | -1500 |  | TBD | 5-7 Days | TBD | ReV PO.030 | 1550 | Sea |  |  | 2026-03-25
Backsheet WCPC (570mm) |  |  |  | 986.7 | 0 | -986.7 |  | TBD | 5-7 Days | TBD | ReV PO.030 | 1140 | Sea |  |  | 2026-03-25 | 2026-05-11 | 1500 (21 May)
Backsheet PET |  |  |  | 87.3 | -15.48 | -102.78 |  | Stock
EVA | First EVA |  |  | 4923 | 0 | -4923 |  | TBD | 10 Days | DP 50% | PO 011 | 6860 | Sea
Interconnect Tab | Xuzhou Xingwen | [6 empty] | TBD | 10 Days | TBD | PO 047
Solar ribbon | Shanghai Fenxiang |  |  | 1.95 | 7.62 | 5.67 |  | 2026-03-06 | 5-7 Days | 2026-03-10 | PO.026 | 40 | Air | Done | SKY Warehouse | 2026-02-07
Busbar |  |  |  | 16.5 | -112.76 | -129.26 |  | 2026-03-06 | 5-7 Days | 2026-03-10 | PO.026 | 281
Junction Box UKT | Go Power |  |  | 1500 | 1550 | 50 |  | Stock
Silicone | Local |  |  | 21 | -127.5 | -148.5 |  | TBD |  | TBD | Open New PO
Label White | Yihe Industry (Local) |  |  | 1500 | 0 | -1500 |  | TBD |  |  | Open New PO
Labels Go Power | Sunshine |  |  | 1500 | 0 | -1500 |  | Stock
High Temp Tape | Mandala Hiba Buana |  |  | 202.5 | 0 | -202.5 |  | TBD |  |  | Open New PO
Master Box | Gilang Wijaya (Local) |  |  | 150 | 0 | -150 |  | TBD |  | TBD | Open New PO
[5 empty] | TH-FPM | DNP |  | 0.98 | 957.6 | 938.448 | 3136 | 3073.28
[5 empty] | TPT |  |  | 1.41 | 1500 | 2115
Consigned raw material | Manufacturer |  |  | Valterra stock Qty till March 13, 2026 by Carson | Valterra Stock Qty till Jan.19, 2026 | Sky Stock till Jan.19, 2026 | Sky Received Jan 24, 2026 | Sky Total Stock Jan.24, 2026 Stock | Qty of Consumption finished goods till March 17, 2026 | Sky Remaining Stock (warehouse+WIP) from Jan to March.17, 2026 | Sky Stock Actual till 13 Mar Warehouse | Sky Actual WIP till March 17, 2026
Cell | Sun Power |  |  | 47530 | 120293 | 120743 | 0 | 120743 | 56240 | 64503 | 47530 | 16973
Cable seal, Weather Pack | TTI |  |  | 10160 | 15000 | 6809 | 15000 | 21809 | 9143 | 12666 | 10160 | 2506
Male Connector | TTI |  |  | 4826 | 11000 | 6829 | 11000 | 17829 | 9143 | 8686 | 4826 | 3860
Connector Dhelpi | TTI |  |  | 6600 | 6600 | 3748 | 6600 | 10348 | 4460 | 5888 | 6600 | -712
Junction Box UKT 110W GP | Suzhou UKT |  |  | 1550 | 1550 | 1550 | 0 | 1550 | 0 | 1550 | 1550 | 0
Junction Box Amphenol 110W TK | Shenzhen Amphenol |  |  | 4200 | 5259 | 5259 | 0 | 5259 | 1200 | 4059 | 4200 | -141
Heliobond PVA-600BT tape 101.6*3mm (with anti sticky) 110W | Kömmerling |  |  | 6660 | 6600 | 6600 | 0 | 6600 | 0 | 6600 | 6660 | -60
Note on I4: Xuming Cai: Sky PO date to suppliers
Note on Q77: Yutio Sapnanda: Need Check Custom Process to Received Before Long Holiday
Note on Q80: Yutio Sapnanda: Eta Port, 12 Mar. Need Prepared Document for Custom Process & Process Payment PIB
Note on Q104: Need Confirm with Supplier & Fedex for Delivery Schedule
Note on Q125: Yutio Sapnanda: Need Confirm Delivery Date
Note on P147: Finish on 18th Mar.
Note on K152: For Gilang Wijaya, Already Paid DP 50% should be enough for 3 PO
Note on A154: Yutio Sapnanda: Start of Phase 2 Order
Note on A167: Yutio Sapnanda: Need Confirm Supplier with Adhelia
Note on G291: Carson Liang: Not included - Sky consumped 50pcs 40W model (cel x 584pcs) in May 20, 2025

## Sheet1 (2) (hidden)
Sky PO Status & Production LT
460pcs 35W PO-609804
Material | Supplier | Contact | Email | QPA | On Hand Inventory | Remaining Inventory | Valterra PO Date | SKY PO Date | Material Production Lead Time | Payment From SKY | SKY PO# | SKY PO Qty | Shipping Method | AWB# or B/L# | Material Location | ETA @SKY | SKY Build Date | SKY Ship Date
Cell | Go Power |  |  | 4906 | 114982 | 110076 | 2025-09-18 | Stock
TPT 350mm | Zhejiang Zec | John Dong | 15858119899@139.com | 460 | 1236 | 776 |  | Stock
Backsheet WCPC |  |  |  | 86.48 | 311.4 | 224.92 |  | Stock
Backsheet PET |  |  |  | 17.48 | 392 | 374.52 |  | Stock
EVA (Front) | Huizhou Baojun | Emma | emma@jsbaojun.cn | 181.24 | 1050 | 868.76 |  | 2026-01-23 | 5-7 Days | 2026-01-26 | PO 008 | 1050 | Air | Done | SKY Warehouse | 2026-02-06 | 2026-02-09
EVA (Back) |  |  |  | 271.86 | 1500 | 1228.14 | [5 empty] | 1500 | Air | Done | SKY Warehouse | 2026-02-06
Solar ribbon | Sunby | Judy Cai | judy@hzdongke.com | 0.74 | 29.44 | 28.7 |  | Stock
Busbar | HZDongke |  |  | 5.06 | 43.42 | 38.36 |  | Stock
Junction Box | China Ruis Industrial | Ben | ben@hongxinxu.com | 460 | 694 | 234 |  | 2025-11-28 | 5-7 Days | 2026-01-14 | PO 090 | 694 | Air | Done | SKY Warehouse | 2026-02-07
Silicone |  |  |  | 11.5 | 164 | 152.5 |  | Stock
Label Silver | Yihe Industry (Local) |  |  | 460 | 6000 | 5540 |  | Stock
Labels TK 35W | Henan Top Run | Grace | toprungrace@sina.cn | 920 | 8000 | 7080 |  | Stock
High Temp Tape | Mandala Hiba Buana |  |  | 5.52 | 302 | 296.48 |  | 2025-12-08 | Ready Stock |  | PO 200 | 3000 | Local | Local | SKY Warehouse | 2026-02-04
Master Box | Gilang Wijaya (Local) |  |  | 16 | 16 | 0 |  | 2026-01-23 | 7 Days | 2026-01-23 | PO 008 |  | Local | Local | SKY Warehouse | 2026-02-04
1000pcs 50W PO-609684
Material | Supplier | Contact | Email | QPA | On Hand Inventory | Remaining Inventory | Valterra PO Date | SKY PO Date | Material Production Lead Time | Payment From SKY | SKY PO# | SKY PO Qty | Shipping Method | AWB# or B/L# | Material Location | ETA @SKY | SKY Build Date | SKY Ship Date
Cell | Go Power |  |  | 15000 | 110076 | 95076 | 2025-05-26 | Stock
TPT 385mm | Zhejiang Zec | John Dong | 15858119899@139.com | 1000 | 2560 | 1560 |  | 2025-12-12 | 5-7 Days | 2026-01-19 | PO 112 | 2060 | Air | Done | SKY Warehouse | 2026-02-06 | 2026-02-10 | 2026-02-14
Backsheet PET |  |  |  | 118 | 374.52 | 256.52 |  | Stock
EVA (Front) | Huizhou Baojun | Emma | emma@jsbaojun.cn | 703 | 868.76 | 165.76 |  | 2026-01-23 | 5-7 Days | 2026-01-26 | PO 009 | 1050 | Air | Done | SKY Warehouse | 2026-02-06
EVA (Back) |  |  |  | 1054.5 | 1228.14 | 173.64 |  |  | 5-7 Days |  | PO 009 | 1500 | Air | Done | SKY Warehouse | 2026-02-06
Solar ribbon | Sunby |  |  | 0.74 | 28.7 | 27.96 |  | Stock
Busbar | HZDongke | Judy Cai | judy@hzdongke.com | 5.06 | 38.36 | 33.3 |  | Stock
Junction Box | China Ruis Industrial | Ben | ben@hongxinxu.com | 1025 | 1264 | 239 |  | 2025-11-28 | 5-7 Days | 2026-01-14 | PO 090 | 1030 | Air | Done | SKY Warehouse | 2026-02-07
Silicone |  |  |  | 25 | 152.5 | 127.5 |  | Stock
Label Silver | Yihe Industry (Local) |  |  | 1000 | 5000 | 4000 |  | Stock
Label Thermolite 50W | Hennan | Grace |  | 1000 | 2280 | 1280 |  | Stock
Labels TK 50W |  |  |  | 1000 | 2280 | 1280 |  | Stock
High Temp Tape | Mandala Hiba Buana |  |  | 95 | 296.48 | 201.48 |  | 2025-12-08 | Ready Stock |  | PO 200 | 3000 | Local | Local | Supplier Warehouse
Master Box | Gilang Wijaya (Local) |  |  | 34 | 0 | -34 |  | 2026-01-23 | 7 Days | 2026-01-23 | PO 008 |  | Local | Local | Supplier Production
1000pcs 50W PO-609784
Material | Supplier | Contact | Email | QPA | On Hand Inventory | Remaining Inventory | Valterra PO Date | SKY PO Date | Material Production Lead Time | Payment From SKY | SKY PO# | SKY PO Qty | Shipping Method | AWB# or B/L# | Material Location | ETA @SKY | SKY Build Date | SKY Ship Date
Cell | Go Power |  |  | 15000 | 95076 | 80076 | 2025-09-02 | Stock
TPT 385mm | Zhejiang Zec | John Dong | 15858119899@139.com | 1000 | 1560 | 560 |  | 2026-02-02 | 5-7 Days | 2026-02-03 | PO 010 | 2100 | Air | Confrim with Fedex | Fedex Warehouse China | 2026-02-18 | 360 Pcs - 14 Feb
Backsheet PET |  |  |  | 118 | 256.52 | 138.52 | [5 empty] | 392
EVA (Front) | Huizhou Baojun | Emma | emma@jsbaojun.cn | 703 | 165.76 | -537.24 |  | 2026-01-29 | 5-7 Days | 2026-02-03 | PO 017 | 2850 | Sea ? | Confrim with FTN | Supplier Warehouse | 2026-03-10
EVA (Back) |  |  |  | 1054.5 | 173.64 | -880.86 | [5 empty] | 3750 |  |  | Supplier Warehouse
EVA | Sveck/EVA Alternative | Maggie |  | 1757.5 | ? | ? |  | 2026-02-09 | 5-7 Days | 2026-02-11 | PO 019 | 2250 | Air | Confrim with Fedex | Supplier Warehouse | 2026-03-01 | 640 Pcs - 3 Mar
[5 empty] | ? | ? | [5 empty] | 4050 | Sea |  | Supplier Warehouse | 2026-03-10
Solar ribbon | Sunby |  |  | 2 | 27.96 | 25.96 |  | Stock
Busbar | HZDongke | Judy Cai | judy@hzdongke.com | 25 | 83.3 | 58.3 |  |  | 5-7 Days | 2026-01-19 | PO 111 | 50 | Air | Done | SKY Warehouse | 2026-02-07
Junction Box ? | China Ruis Industrial | Ben | ben@hongxinxu.com | 1025 | 1269 | 244 |  | 2025-11-28 | 5-7 Days | 2026-01-14 | PO 090 | 1030 | Air | Done | SKY Warehouse | 2026-02-07
Silicone |  |  |  | 25 | 127.5 | 102.5 |  | Stock
Label Thermolite 50W | Hennan | Grace |  | 1000 | 1280 | 280 |  | 2026-01-12 | 4 Days | 2026-02-05 | PO 012 | 5250 | DHL |  | Supplier Warehouse
Labels TK 50W |  |  |  | 1000 | 1280 | 280 |  |  |  |  | PO 012 | 5250 | DHL |  | Supplier Warehouse
High Temp Tape | Mandala Hiba Buana |  |  | 95 | 201.48 | 106.48 |  | 2025-12-08 | Ready Stock |  | PO 200 | 3000 | Local | Local | Supplier Warehouse
Master Box | Gilang Wijaya (Local) |  |  | 34 | 0 | -34 |  | 2026-01-23 | 7 Days | 2026-01-23 | PO 008 |  | Local | Local | Supplier Production
2000pcs 35W PO-609820 | Part 1
Material | Supplier | Contact | Email | QPA | On Hand Inventory | Remaining Inventory | Valterra PO Date | SKY PO Date | Material Production Lead Time | Payment From SKY | SKY PO# | SKY PO Qty | Shipping Method | AWB# or B/L# | Material Location | ETA @SKY | SKY Build Date | SKY Ship Date
Cell | Go Power |  |  | 21334 | 80076 | 58742 | 2025-10-02 | Stock
TPT 350mm | Zhejiang Zec | John Dong | 15858119899@139.com | 2000 | 776 | -1224 |  | 2026-02-02 | 5-7 Days | 2026-02-03 | PO 010 | 2100 | Air | Confrim with Fedex | Fedex Warehouse China | 2026-02-18
Backsheet WCPC |  |  |  | 376 | 224.92 | -151.08 | [5 empty] | 660
Backsheet PET |  |  |  | 76 | 138.52 | 62.52 | [5 empty] | 392
EVA (Front) | Huizhou Baojun | Emma | emma@jsbaojun.cn | 788 | -537.24 | -1325.24 |  | 2026-01-29 | 5-7 Days | 2026-02-03 | PO 017 | 2850 | Sea ? | Confrim with FTN | Supplier Warehouse | 2026-03-10
EVA (Back) |  |  |  | 1182 | -880.86 | -2062.86 | [5 empty] | 3750 |  |  | Supplier Warehouse
EVA | Sveck/EVA Alternative | Maggie |  | 1970 | ? | ? |  | 2026-02-09 | 5-7 Days | 2026-02-11 | PO 019 | 2250 | Air | Confrim with Fedex | Supplier Warehouse | 2026-03-01
[5 empty] | ? | ? | [5 empty] | 4050 | Sea |  | Supplier Warehouse | 2026-03-10
Solar ribbon | Sunby |  |  | 3.2 | 25.96 | 22.76 |  | Stock
Busbar | HZDongke | Judy Cai | judy@hzdongke.com | 22 | 58.3 | 36.3 |  |  | 5-7 Days | 2026-01-19 | PO 111 | 50 | Air | Done | SKY Warehouse | 2026-02-07
Junction Box | China Ruis Industrial | Ben | ben@hongxinxu.com | 2050 | 244 | -1806 |  | 2026-02-02 | 5-7 Days | Not Paid | PO 013 | 3240 | Air | Confrim with Fedex | Supplier Production | 2026-03-05 | 2026-03-11
Silicone |  |  |  | 50 | 102.5 | 52.5 |  | Stock
Label Silver | Yihe Industry (Local) |  |  | 2000 | 5540 | 3540 |  | Stock
Labels TK 35W | Henan |  |  | 2000 | 7080 | 5080 |  | 2026-01-12 | 4 Days | 2026-02-05 | PO 012 | 8000 |  |  | Supplier Warehouse
High Temp Tape | Mandala Hiba Buana |  |  | 95 | 106.48 | 11.48 |  | 2025-12-08 | Ready Stock |  | PO 200 | 3000 | Local | Local | Supplier Warehouse
Master Box | Gilang Wijaya (Local) |  |  | 67 | 0 | -67 |  | 2026-01-23 | 7 Days | Not paid | PO 008 |  | Local | Local | Supplier Production
1000pcs 50W PO-609880
Material | Supplier | Contact | Email | QPA | On Hand Inventory | Remaining Inventory | Valterra PO Date | SKY PO Date | Material Production Lead Time | Payment From SKY | SKY PO# | SKY PO Qty | Shipping Method | AWB# or B/L# | Material Location | ETA @SKY | SKY Build Date | SKY Ship Date
Cell | Go Power |  |  | 15000 | 58742 | 43742 | 2025-11-18 | Stock
TPT 385mm | Zhejiang Zec | John Dong | 15858119899@139.com | 1000 | 560 | -440 |  | 2026-02-02 | 5-7 Days | 2026-02-03 | PO 010 | 2100 | Air | Confrim with Fedex | Fedex Warehouse
Backsheet PET |  |  |  | 118 | 62.52 | -55.48 | [5 empty] | 392
EVA (Front) | Huizhou Baojun | Emma | emma@jsbaojun.cn | 703 | -537.24 | -1240.24 |  | 2026-01-29 | 5-7 Days | 2026-02-03 | PO 017 | 2850 | Sea | Confrim with FTN | Supplier Warehouse | 2026-03-10
EVA (Back) |  |  |  | 1054.5 | -880.86 | -1935.36 | [5 empty] | 3750 |  |  | Supplier Warehouse
EVA | Sveck/EVA Alternative | Maggie |  | 1757.5 | ? | ? |  | 2026-02-09 | 5-7 Days | 2026-02-11 | PO 019 |  | Air | Confrim with Fedex | Supplier Warehouse | 2026-03-01
[5 empty] | ? | ? | [6 empty] | Sea |  | Supplier Warehouse | 2026-03-10
Solar ribbon | Sunby |  |  | 2 | 22.76 | 20.76 |  | Stock
Busbar | HZDongke | Judy Cai | judy@hzdongke.com | 25 | 36.3 | 11.3 |  |  | 5-7 Days | 2026-01-19 | PO 111 | 50 | Air | Done | SKY Warehouse | 2026-02-07
Junction Box | China Ruis Industrial | Ben | ben@hongxinxu.com | 1025 | -1806 | -2831 |  | 2026-02-02 | 5-7 Days | Not Paid | PO 013 | 3240 | Sea | Confrim with FTN | Supplier Production | 2026-03-15 | 2026-03-16
Silicone |  |  |  | 25 | 52.5 | 27.5 |  | Stock
Label Thermolite 50W | Henan | Grace |  | 1000 | 280 | -720 |  | 2026-01-12 | 4 Days | 2026-02-05 | PO 012
Labels TK 50W |  |  |  | 1000 | 280 | -720 |  |  | 4 Days |  | PO 012 |  |  |  | Supplier Warehouse
High Temp Tape | Mandala Hiba Buana |  |  | 95 | 106.48 | 11.48 |  | 2025-12-08 | Ready Stock |  | PO 200 | 3000 | Local | Local | Supplier Warehouse
Master Box | Gilang Wijaya (Local) |  |  | 34 | 0 | -34 |  | 2026-01-23 | 7 Days | Not paid | PO 008 |  | Local | Local | Supplier Production
2000pcs 35W PO-609820 | Part 2
Material | Supplier | Contact | Email | QPA | On Hand Inventory | Remaining Inventory | Valterra PO Date | SKY PO Date | Material Production Lead Time | Payment From SKY | SKY PO# | SKY PO Qty | Shipping Method | AWB# or B/L# | Material Location | ETA @SKY | SKY Build Date | SKY Ship Date
Cell | Go Power |  |  | 21334 | 43742 | 22408 |  | Stock
TPT 350mm | Zhejiang Zec | John Dong | 15858119899@139.com | 2000 | -1224 | -3224 |  | 2026-02-02 | 5-7 Days | 2026-02-03 | PO 010 | 2100 | Air | Confrim with Fedex | Fedex Warehouse China | 2026-02-18
Backsheet WCPC |  |  |  | 86.48 | -151.08 | -237.56 | [5 empty] | 660
Backsheet PET |  |  |  | 76 | -55.48 | -131.48 | [5 empty] | 392
EVA (Front) | Huizhou Baojun | Emma | emma@jsbaojun.cn | 788 | -1240.24 | -2028.24 |  | 2026-01-29 | 5-7 Days | 2026-02-03 | PO 017 | 2850 | Sea ? | Confrim with FTN | Supplier Warehouse | 2026-03-10
EVA (Back) |  |  |  | 1182 | -1935.36 | -3117.36 | [5 empty] | 3750 |  |  | Supplier Warehouse
EVA | Sveck/EVA Alternative | Maggie |  | 1970 | ? | ? |  | 2026-02-09 |  | 2026-02-11 | PO 019 |  | Air | Confrim with Fedex | Supplier Warehouse | 2026-03-01
[5 empty] | ? | ? | [6 empty] | Sea |  | Supplier Warehouse | 2026-03-10
Solar ribbon | Sunby |  |  | 3.2 | 20.76 | 17.56 |  | Stock
Busbar | HZDongke | Judy Cai | judy@hzdongke.com | 22 | 11.3 | -10.7 |  |  | 5-7 Days | 2026-01-19 | PO 111 | 50 | Air | Done | SKY Warehouse | 2026-02-07
Junction Box | China Ruis Industrial | Ben | ben@hongxinxu.com | 2050 | -2831 | -4881 |  | 2026-02-02 | 5-7 Days | Not Paid | PO 013 | 3240 | Air | Confrim with Fedex | Supplier Production | 2026-03-05 | 2026-03-11
Silicone |  |  |  | 50 | 27.5 | -22.5 |  | Stock
Label Silver | Yihe Industry (Local) |  |  | 2000 | 3540 | 1540 |  | Stock
Labels TK 35W | Henan |  |  | 2000 | 5080 | 3080 |  | 2026-01-12 | 4 Days | 2026-02-05 | PO 009
High Temp Tape | Mandala Hiba Buana |  |  | 95 | 11.48 | -83.52 |  | 2025-12-08 | Ready Stock | Not paid | PO 200 |  | Local | Local
Master Box | Gilang Wijaya (Local) |  |  | 67 | 0 | -67 |  | 2026-01-23 | 7 Days | Not paid | PO 008 |  | Local | Local
1500pcs110W PO-609614
Material | Supplier | Contact | Email | QPA | On Hand Inventory | Remaining Inventory | Valterra PO Date | SKY PO Date | Material Production Lead Time | Payment From SKY | SKY PO# | SKY PO Qty | Shipping Method | AWB# or B/L# | Material Location | ETA @SKY | SKY Build Date | SKY Ship Date
Cell | Go Power |  |  | 48000 | 22408 | -25592
TPT | Zhejiang Zec | John Dong | 15858119899@139.com | 1500 |  | -1500
Backsheet WCPC |  |  |  | 986.7 |  | -986.7 | [5 empty] | 660
Backsheet PET |  |  |  | 87.3 | -131.48 | -218.78
EVA (Front) | Huizhou Baojun | Emma | emma@jsbaojun.cn |  |  | 0
EVA (Back) | [5 empty] | 0
EVA | Sveck/EVA Alternative | Maggie |  |  |  | ?
?
Solar ribbon | Sunby |  |  |  |  | 0
Busbar | HZDongke | Judy Cai | judy@hzdongke.com |  |  | 0
Junction Box UKT | [5 empty] | 0
Silicone | [5 empty] | 0
Label Silver | Yihe Industry (Local) |  |  |  |  | 0
Labels Go Power | Sunshine |  |  |  |  | 0
High Temp Tape | Mandala Hiba Buana |  |  |  |  | 0
Master Box | Gilang Wijaya (Local) |  |  |  |  | 0
1000pcs 50W PO-609900
Material | Supplier | Contact | Email | QPA | On Hand Inventory | Remaining Inventory | Valterra PO Date | SKY PO Date | Material Production Lead Time | Payment From SKY | SKY PO# | SKY PO Qty | Shipping Method | AWB# or B/L# | Material Location | ETA @SKY | SKY Build Date | SKY Ship Date
Cell | Go Power |  |  | 15000
TPT 385mm | Zhejiang Zec | John Dong | 15858119899@139.com | 1000
Backsheet PET |  |  |  | 118
EVA (Front) | Huizhou Baojun | Emma | emma@jsbaojun.cn | 703
EVA (Back) |  |  |  | 1054.5
EVA (Front) | Sveck/EVA Alternative | Maggie |  | 1757.5
EVA (Back)
Solar ribbon | Sunby |  |  | 2
Busbar | HZDongke | Judy Cai | judy@hzdongke.com | 25
Junction Box | China Ruis Industrial | Ben | ben@hongxinxu.com | 1025
Silicone |  |  |  | 25
Label Thermolite 50W | Henan | Grace |  | 1000
Labels TK 50W |  |  |  | 1000
High Temp Tape | Mandala Hiba Buana |  |  | 95
Master Box | Gilang Wijaya (Local) |  |  | 34
2000pcs 35W PO-609915
Material | Supplier | Contact | Email | QPA | On Hand Inventory | Remaining Inventory | Valterra PO Date | SKY PO Date | Material Production Lead Time | Payment From SKY | SKY PO# | SKY PO Qty | Shipping Method | AWB# or B/L# | Material Location | ETA @SKY | SKY Build Date | SKY Ship Date
Cell | Go Power |  |  | 21334
TPT 350mm | Zhejiang Zec | John Dong | 15858119899@139.com | 2000
Backsheet WCPC |  |  |  | 86.48
Backsheet PET |  |  |  | 76
EVA (Front) | Huizhou Baojun | Emma | emma@jsbaojun.cn | 788
EVA (Back) |  |  |  | 1182
EVA | Sveck/EVA Alternative | Maggie |  | 1970
Solar ribbon | Sunby |  |  | 3.2
Busbar | HZDongke | Judy Cai | judy@hzdongke.com | 22
Junction Box | China Ruis Industrial | Ben | ben@hongxinxu.com | 2050
Silicone |  |  |  | 50
Label Silver | Yihe Industry (Local) |  |  | 2000
Labels TK 35W | Henan |  |  | 2000
High Temp Tape | Mandala Hiba Buana |  |  | 95
Master Box | Gilang Wijaya (Local) |  |  | 67
5pcs 30W 3-diode PO-609915
Material | Supplier | Contact | Email | QPA | On Hand Inventory | Remaining Inventory | Valterra PO Date | SKY PO Date | Material Production Lead Time | Payment From SKY | SKY PO# | SKY PO Qty | Shipping Method | AWB# or B/L# | Material Location | ETA @SKY | SKY Build Date | SKY Ship Date
Cell | Go Power |  |  | 21334
TPT 350mm | Zhejiang Zec | John Dong | 15858119899@139.com | 2000
Backsheet WCPC |  |  |  | 86.48
Backsheet PET |  |  |  | 76
EVA (Front) | Huizhou Baojun | Emma | emma@jsbaojun.cn | 788
EVA (Back) |  |  |  | 1182
EVA | Sveck/EVA Alternative | Maggie |  | 1970
Solar ribbon | Sunby |  |  | 3.2
Busbar | HZDongke | Judy Cai | judy@hzdongke.com | 22
Junction Box | China Ruis Industrial | Ben | ben@hongxinxu.com | 2050
Silicone |  |  |  | 50
Label Silver | Yihe Industry (Local) |  |  | 2000
Labels TK 35W | Henan |  |  | 2000
High Temp Tape | Mandala Hiba Buana |  |  | 95
Master Box | Gilang Wijaya (Local) |  |  | 67
2000pcs 50W PO-609926
Material | Supplier | Contact | Email | QPA | On Hand Inventory | Remaining Inventory | Valterra PO Date | SKY PO Date | Material Production Lead Time | Payment From SKY | SKY PO# | SKY PO Qty | Shipping Method | AWB# or B/L# | Material Location | ETA @SKY | SKY Build Date | SKY Ship Date
Cell | Go Power |  |  | 30000
TPT 385mm | Zhejiang Zec | John Dong | 15858119899@139.com | 2000
Backsheet PET |  |  |  | 236
EVA (Front) | Huizhou Baojun | Emma | emma@jsbaojun.cn | 1406
EVA (Back) |  |  |  | 2109
EVA (Front) | Sveck/EVA Alternative | Maggie |  | 3515
EVA (Back)
Solar ribbon | Sunby |  |  | 4
Busbar | HZDongke | Judy Cai | judy@hzdongke.com | 50
Junction Box | China Ruis Industrial | Ben | ben@hongxinxu.com | 2050
Silicone |  |  |  | 50
Label Thermolite 50W | Henan | Grace |  | 2000
Labels TK 50W |  |  |  | 2000
High Temp Tape | Mandala Hiba Buana |  |  | 190
Master Box | Gilang Wijaya (Local) |  |  | 67
1000pcs 50W PO-609945
Material | Supplier | Contact | Email | QPA | On Hand Inventory | Remaining Inventory | Valterra PO Date | SKY PO Date | Material Production Lead Time | Payment From SKY | SKY PO# | SKY PO Qty | Shipping Method | AWB# or B/L# | Material Location | ETA @SKY | SKY Build Date | SKY Ship Date
Cell | Go Power |  |  | 15000
TPT 385mm | Zhejiang Zec | John Dong | 15858119899@139.com | 1000
Backsheet PET |  |  |  | 118
EVA (Front) | Huizhou Baojun | Emma | emma@jsbaojun.cn | 703
EVA (Back) |  |  |  | 1054.5
EVA (Front) | Sveck/EVA Alternative | Maggie |  | 1757.5
EVA (Back)
Solar ribbon | Sunby |  |  | 2
Busbar | HZDongke | Judy Cai | judy@hzdongke.com | 25
Junction Box | China Ruis Industrial | Ben | ben@hongxinxu.com | 1025
Silicone |  |  |  | 25
Label Thermolite 50W | Henan | Grace |  | 1000
Labels TK 50W |  |  |  | 1000
High Temp Tape | Mandala Hiba Buana |  |  | 95
Master Box | Gilang Wijaya (Local) |  |  | 34
Note on I4: Xuming Cai: Sky PO date to suppliers
Note on K58: SKY PO only 2100 Qty for TPT, Not enough to fulfill this Order
Note on K72: For Gilang Wijaya, Already Paid DP 50% should be enough for 3 PO
Note on K77: TPT should not be enough for this PO
Note on K95: SKY PO only 2100 Qty for TPT, Not enough to fulfill this Order
Note on K109: For Gilang Wijaya, Already Paid DP 50% should be enough for 3 PO
Note on K165: For Gilang Wijaya, Already Paid DP 50% should be enough for 3 PO
Note on K184: For Gilang Wijaya, Already Paid DP 50% should be enough for 3 PO