## Valterra Schdule
VALTERRA PROJECT
PLANNING ARRIVAL MATERIAL & DELIVERY PRODUCT
Material Arrange | [16 empty] | 2026
[8 empty] | January |  |  |  |  | February |  |  |  | March | [9 empty] | April | [11 empty] | May | [7 empty] | June
[8 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 |  |  | 12 |  | 13 | 14 |  |  | 15 |  |  | 16 |  |  | 17 |  |  |  | 18 |  | 19 |  |  | 20 |  | 21 | 22 |  | 23 | 24 | 25 | 26
[6 empty] | Payment Material | : | [11 empty] | PO.9820, 9880, 9614 & 9915 | [6 empty] | PO.9900,9926 & 9945
[6 empty] | Production Material (Supplier) | :
|  |  |  | Delivery Material |  | Air | : | [14 empty] | TPT 35W 2100
[6 empty] | Sea | : | [14 empty] | All Material Import | [6 empty] | All Material Import
[6 empty] | Arrival Material | :
[6 empty] | Incoming Check Material | :
No | Detailed Project Order
| Order |  | Type |  | Qty
1 | PO.9684 | No.5 | 82882-C | 50 | 1000
[6 empty] | Delivery Product : | [13 empty] | 40 pcs
2 | PO.9784 | No.7 | 82882-C | 50 | 1000
[6 empty] | Delivery Product : | [13 empty] | 140 pcs | [11 empty] | 360 pcs |  |  | 500 pcs
3 | PO.9820 | No.8 | 1 Diode | 35 | 500
[6 empty] | Delivery Product : | [12 empty] | 180 pcs
4 | PO.9820 | No.8 | 1 Diode | 35 | 1500
[6 empty] | Delivery Product : | [13 empty] | 540 pcs |  |  |  |  | 540 pcs |  |  | 420 PCS
5 | PO.9820 | No.8 | 1 Diode | 35 | 2000
[6 empty] | Delivery Product : | [21 empty] | 210 PCS |  |  | 1350 pcs |  |  | 440 PCS
6 | PO.9880 | No.9 | 82882-C | 50 | 1000
[6 empty] | Delivery Product : | [29 empty] | 1000 PCS
7 | PO.9614 | No.4 |  | 110 | 1500
[6 empty] | Delivery Product : | [31 empty] | 1500 PCS
8 | PO.9900 | No.10 | 82882-C | 50 | 1000
[6 empty] | Delivery Product : | [33 empty] | 1000 PCS
9 | PO.9915 | No.11 | 3 Diode | 35 | 2000
[6 empty] | Delivery Product : | [34 empty] | 1000 PCS |  | 1000 PCS
10 | PO.9926 | No.12 | 82882-C | 50 | 2000
[6 empty] | Delivery Product : | [37 empty] | 1000 PCS | 1000 PCS
11 | PO.9945 | No.13 | 82882-C | 50 | 1000
[6 empty] | Delivery Product : | [39 empty] | 1000 PCS
Note :

## Valterra 26 Feb (hidden)
j
Summary Delivery Schedule
Customer : Valterra
| No. | Company |  | Panel | Quantity |  | Oct-25 |  |  |  |  | Nov-25 |  |  |  |  | Material 800 Pcs 295W |  |  |  | Oct-25 |  |  |  | Oct-25
[7 empty] | 40 | 41 | 42 | 42 |  | 44 | 45 | 46 | 47 | [5 empty] | 40 | 41 | 42 | 43 | 40 | 41 | 42 | 43
| 1 | IconGreen |  | 295W Panel | 1500 |  |  |  | 800 | 800 | [6 empty] | Materials |  | Detail | Amount | Oct-25 42: 800; Oct-25 43: 700; Oct-25 42: 800; Oct-25 43: 700 | Due Date
[9 empty] | 24 Oct | 24 Oct | [6 empty] | 295W Module |  | PIB+Penalty | 110000000 | Oct-25 42: 24 Oct; Oct-25 43: 31 Oct; Oct-25 42: 24 Oct; Oct-25 43: 31 Oct | This week |  | 150 | 2025-10-31
[12 empty] | 540 |  |  |  |  | Potting Gel |  | PIB | 500000 | Oct-25 43: 150; Oct-25 43: 150 | 2025-10-27 |  | 300 | 2025-11-05
[12 empty] | Beg Nov |  |  |  |  | Masterbox |  | DP | 15000000 | Oct-25 43: 31 Oct; Oct-25 43: 31 Oct | This week |  | 240 | 2025-11-07
Feb 20th Schedule
Internal No | No. | Company | PO | Panel | PO Qty | Month | 2026-01-01 |  |  |  |  | Feb-26 |  |  |  | Mar-26 |  |  |  |  | Oct-25 40: 2026-04-01; Oct-25 40: 2026-05-01 | Total
[6 empty] | Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
5 | 1 | Valterra | PO609684 | 50W | 1000 | Qty | Feb-26 7: 540; Feb-26 8: 420; Mar-26 10: 40; Mar-26 13: Eid Al-Fitr Holiday |  | 5
[6 empty] | Date | Feb-26 7: 14 Feb; Feb-26 8: 21 Feb; Mar-26 10: TBD |  |  | 150 | 2025-10-31
6 | 2 |  | PO609804 | 35W | 1000 | Qty | 2026-01-01 3: 30; 2026-01-01 4: 90; Feb-26 6: 420; Feb-26 7: 450; Feb-26 8: 10 |  | 6
[6 empty] | Date | 2026-01-01 3: 16 Jan; 2026-01-01 4: 24 Jan; Feb-26 6: 5 Feb; Feb-26 7: 13 Feb; Feb-26 8: 21 Feb
7 | 3 |  | PO609784 | 50W | 1000 | Qty | Mar-26 12: 500; Mar-26 14: 500 |  | 7
[6 empty] | Date | Mar-26 12: TBD; Mar-26 14: TBD
8 | 4 |  | PO609820 | 35W | 4000 | Qty | Feb-26 8: 320; Mar-26 10: 180; Mar-26 11: 540; Mar-26 12: 720; Mar-26 14: 240; 2026-04-01 15: 1200; 2026-04-01 16: 800 |  | 8
[6 empty] | Date | Feb-26 8: 21 Feb; Mar-26 10: TBD; Mar-26 11: TBD; Mar-26 12: TBD; Mar-26 14: TBD; 2026-04-01 15: TBD; 2026-04-01 16: TBD
9 | 5 |  | PO609880 | 50W | 1000 | Qty | Mar-26 14: 500; 2026-04-01 15: 500 |  | 9
[6 empty] | Date | Mar-26 14: TBD; 2026-04-01 15: TBD
4 | 6 |  | PO609614 | 110W | 1500 | Qty | 2026-04-01 16: 900; 2026-04-01 17: 600 |  | 4
[6 empty] | Date | 2026-04-01 16: TBD; 2026-04-01 17: TBD
10 | 7 |  | PO609900 | 50W | 1000 | Qty | 2026-04-01 17: 1000 |  | 10
[6 empty] | Date | 2026-04-01 17: TBD
11 | 8 |  | PO609915 | 35W | 2000 | Qty | 2026-04-01 18: 2000 |  | 11
[6 empty] | Date | 2026-04-01 18: TBD
|  |  |  | 30W 3 Diode | 5 | Qty | Mar-26 10: 5
[6 empty] | Date | Mar-26 10: TBD
12 | 9 |  | PO609926 | 50W | 2000 | Qty | 2026-05-01 19: 2000 |  | 12
[6 empty] | Date | 2026-05-01 19: TBD
13 | 10 |  | PO609945 | 50W | 1000 | Qty | 2026-05-01 20: 1000 |  | 13
[6 empty] | Date | 2026-05-01 20: TBD
16900 |  | Salary Payment |  |  |  | Working Day | [5 empty] | Paid | Paid | 3 | 5 | 6 | 6 | 2 |  | 4 | 4 | 5 | 6 | 6 | 6 | 5 |  |  | 58
[6 empty] | Cost | [7 empty] | 3195.2663 | 5520.8873 | 6625.0647 | 6625.0647 | 2208.3549 |  | 4416.7098 | 4416.7098 | 5520.8873 | 6625.0647 | 6625.0647 | 6625.0647 | 5520.8873 | 0 | 0 | 63925.0263
| Schedule |  |  | Status | Oct |  | 2026-01-01 3: Nov; 2026-04-01 17: Nov; 2026-05-01 21: Nov
[5 empty] | W1 |  | W3 | W4 | W1 | W1 |  | W3 | W4 | [7 empty] | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2
J-Leaf 295 Wp (1,500 pcs)
|  | Material Procurement |  | TBC
|  | Delivery Raw Material |  | 17 | [9 empty] | #REF! | bar: Nov W1 to Nov W2; Nov W1 to Nov W2
|  | Production |  | TBC
|  | Delivery to CMWI | [5 empty] | 150 | 540 | 540 |  | 390 | 420 | [7 empty] | W4: 150; Nov W1: 540; Nov W4: 150; Nov W1: 540
Feb 10th Schedule
Internal No | No. | Company | PO | Panel | PO Qty | Month | 2026-01-01 |  |  |  |  | Feb-26 |  |  |  | Mar-26 |  |  |  |  | W3: 2026-04-01; Nov W3: 2026-05-01
[6 empty] | Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
5 | 1 | Valterra | PO609684 | 50W | 1000 | Qty | Feb-26 7: 540; Feb-26 8: 460; Mar-26 13: Eid Al-Fitr Holiday |  | 5
[6 empty] | Date | Feb-26 7: 2nd Week; Feb-26 8: 3rd Week |  |  | 150 | 2025-10-31
6 | 2 |  | PO609804 | 35W | 1000 | Qty | 2026-01-01 3: 30; 2026-01-01 4: 90; Feb-26 6: 420; Feb-26 7: 450; Feb-26 8: 10 |  | 6
[6 empty] | Date | 2026-01-01 3: 16 Jan; 2026-01-01 4: 24 Jan; Feb-26 6: 5 Feb; Feb-26 7: 2nd Week; Feb-26 8: 3rd Week
7 | 3 |  | PO609784 | 50W | 1000 | Qty | Feb-26 9: 720; Mar-26 10: 280 |  | 7
[6 empty] | Date | Feb-26 9: End Feb; Mar-26 10: 1st Week
8 | 4 |  | PO609820 | 35W | 4000 | Qty | Feb-26 8: 500; Mar-26 11: 1260; Mar-26 14: 240; 2026-04-01 15: 2000 |  | 8
[6 empty] | Date | Feb-26 8: 3rd Week; Mar-26 11: 2nd Week; Mar-26 14: End Mar; 2026-04-01 15: 1st Week
9 | 5 |  | PO609880 | 50W | 1000 | Qty | Mar-26 14: 1000 |  | 9
[6 empty] | Date | Mar-26 14: End Mar
4 | 6 |  | PO609614 | 110W | 1500 | Qty | 2026-04-01 16: 1500 |  | 4
[6 empty] | Date | 2026-04-01 16: 2nd Week
10 | 7 |  | PO609900 | 50W | 1000 | Qty | 2026-04-01 17: 1000 |  | 10
[6 empty] | Date | 2026-04-01 17: 3rd Week
11 | 8 |  | PO609915 | 35W | 2000 | Qty | 2026-04-01 18: 2000 |  | 11
[6 empty] | Date | 2026-04-01 18: End Apr
|  |  |  | 30W 3 Diode | 5 | Qty | Mar-26 10: 5
[6 empty] | Date | Mar-26 10: 1st Week
12 | 9 |  | PO609926 | 50W | 2000 | Qty | 2026-05-01 19: 2000 |  | 12
[6 empty] | Date | 2026-05-01 19: 1st Week
13 | 10 |  | PO609945 | 50W | 1000 | Qty | 2026-05-01 20: 1000 |  | 13
[6 empty] | Date | 2026-05-01 20: 2nd Week
Feb 4th Schedule
| No. | Company | PO | Panel | PO Qty | Month | 2026-01-01 1: 2026-01-01; Feb-26 6: Feb-26; Mar-26 10: Mar-26; 2026-04-01 15: 2026-04-01; 2026-05-01 19: 2026-04-01
[6 empty] | Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 15 | 16 | 17 | 18
| 1 | Valterra | PO609684 | 50W | 1000 | Qty | Feb-26 7: 1000; Mar-26 13: Eid Al-Fitr Holiday
[6 empty] | Date | Feb-26 7: 2nd Week
| 2 |  | PO609804 | 35W | 1000 | Qty | 2026-01-01 3: 30; 2026-01-01 4: 90; Feb-26 6: 420; Feb-26 7: 460
[6 empty] | Date | 2026-01-01 3: 16 Jan; 2026-01-01 4: 24 Jan; Feb-26 6: 1st Week; Feb-26 7: 2nd Week
| 3 |  | PO609784 | 50W | 1000 | Qty | Feb-26 8: 1000
[6 empty] | Date | Feb-26 8: 3rd Week
| 4 |  | PO609820 | 35W | 4000 | Qty | Feb-26 8: 680; Feb-26 9: 1320; Mar-26 10: 540; Mar-26 11: 1460
[6 empty] | Date | Feb-26 8: 3rd Week; Feb-26 9: End Feb; Mar-26 10: 1st Week; Mar-26 11: 2nd Week
| 5 |  | PO609880 | 50W | 1000 | Qty | Feb-26 9: 180; Mar-26 10: 820
[6 empty] | Date | Feb-26 9: End Feb; Mar-26 10: 1st Week
| 6 |  | PO609614 | 110W | 1500 | Qty | Mar-26 12: 720; Mar-26 14: 780
[6 empty] | Date | Mar-26 12: 3rd Week; Mar-26 14: End Mar
| 7 |  | PO609900 | 50W | 1000 | Qty | 2026-04-01 15: 500; 2026-04-01 16: 500; 2026-04-01 15: 500; 2026-04-01 16: 500
[6 empty] | Date | 2026-04-01 15: 1st Week; 2026-04-01 16: 2nd Week; 2026-04-01 15: 1st Week; 2026-04-01 16: 2nd Week
| 8 |  | PO609915 | 35W | 2000 | Qty | 2026-04-01 16: 1000; 2026-04-01 17: 1000; 2026-04-01 16: 1000; 2026-04-01 17: 1000
[6 empty] | Date | 2026-04-01 16: 2nd Week; 2026-04-01 17: 3rd Week; 2026-04-01 16: 2nd Week; 2026-04-01 17: 3rd Week
|  |  |  | 30W 3 Diode | 5 | Qty | Feb-26 8: 5
[6 empty] | Date | Feb-26 8: 3rd Week
| 9 |  | PO609926 | 50W | 2000 | Qty | 2026-04-01 17: 1000; 2026-04-01 18: 1000; 2026-04-01 17: 1000; 2026-04-01 18: 1000
[6 empty] | Date | 2026-04-01 17: 3rd Week; 2026-04-01 18: End Apr; 2026-04-01 17: 3rd Week; 2026-04-01 18: End Apr
| 10 |  | PO609945 | 50W | 1000 | Qty | 2026-04-01 18: 1000; 2026-04-01 18: 1000
[6 empty] | Date | 2026-04-01 18: End Apr; 2026-04-01 18: End Apr
[7 empty] | 2026-04-01 18: Total IDR : | 1080332945

## Valterra 03 March
j
Summary Delivery Schedule
Customer : Valterra
| No. | Company |  | Panel | Quantity |  | Oct-25 |  |  |  |  | Nov-25 |  |  |  |  | Material 800 Pcs 295W |  |  |  | Oct-25 |  |  |  | Oct-25
[7 empty] | 40 | 41 | 42 | 42 |  | 44 | 45 | 46 | 47 | [5 empty] | 40 | 41 | 42 | 43 | 40 | 41 | 42 | 43
| 1 | IconGreen |  | 295W Panel | 1500 |  |  |  | 800 | 800 | [6 empty] | Materials |  | Detail | Amount | Oct-25 42: 800; Oct-25 43: 700; Oct-25 42: 800; Oct-25 43: 700 | Due Date
[9 empty] | 24 Oct | 24 Oct | [6 empty] | 295W Module |  | PIB+Penalty | 110000000 | Oct-25 42: 24 Oct; Oct-25 43: 31 Oct; Oct-25 42: 24 Oct; Oct-25 43: 31 Oct | This week |  | 150 | 2025-10-31
[12 empty] | 540 |  |  |  |  | Potting Gel |  | PIB | 500000 | Oct-25 43: 150; Oct-25 43: 150 | 2025-10-27 |  | 300 | 2025-11-05
[12 empty] | Beg Nov |  |  |  |  | Masterbox |  | DP | 15000000 | Oct-25 43: 31 Oct; Oct-25 43: 31 Oct | This week |  | 240 | 2025-11-07
Update, 10 March 2026
Internal No | No. | Company | PO | Panel | PO Qty | Month | 2026-01-01 |  |  |  |  | Feb-26 |  |  |  | Mar-26 |  |  |  |  | Oct-25 40: 2026-04-01; Oct-25 40: 2026-05-01 | Total
[6 empty] | Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
5 | 1 | Valterra | PO609684 | 50W | 1000 | Qty | Feb-26 7: 540; Feb-26 8: 420; Mar-26 11: 40; Mar-26 13: Eid Al-Fitr Holiday |  | 5
[6 empty] | Date | Feb-26 7: 14 Feb; Feb-26 8: 21 Feb; Mar-26 11: 2026-03-11 |  |  | 150 | 2025-10-31
6 | 2 |  | PO609804 | 35W | 1000 | Qty | 2026-01-01 3: 30; 2026-01-01 4: 90; Feb-26 6: 420; Feb-26 7: 450; Feb-26 8: 10 |  | 6
[6 empty] | Date | 2026-01-01 3: 16 Jan; 2026-01-01 4: 24 Jan; Feb-26 6: 5 Feb; Feb-26 7: 13 Feb; Feb-26 8: 21 Feb
7 | 3 |  | PO609784 | 50W | 1000 | Qty | Mar-26 11: 140; Mar-26 12: 360; Mar-26 14: 500 |  | 7
[6 empty] | Date | Mar-26 11: 2026-03-11; Mar-26 12: 2026-03-16; Mar-26 14: 2026-03-27
8 | 4 |  | PO609820 | 35W | 4000 | Qty | Feb-26 8: 320; Mar-26 10: 180; Mar-26 11: 540; Mar-26 12: 900; Mar-26 14: 540; 2026-04-01 15: 720; 2026-04-01 16: 800 |  | 8
[6 empty] | Date | Feb-26 8: 21 Feb; Mar-26 10: 2026-03-07; Mar-26 11: 2026-03-14; Mar-26 12: 2026-03-16; Mar-26 14: 2026-03-27; 2026-04-01 15: 2026-04-03; 2026-04-01 16: 2026-04-09
9 | 5 |  | PO609880 | 50W | 1000 | Qty | 2026-04-01 16: 1000 |  | 9
[6 empty] | Date | 2026-04-01 16: 2026-04-11
4 | 6 |  | PO609614 | 110W | 1500 | Qty | 2026-05-01 21: 1000 |  | 4
[6 empty] | Date | 2026-05-01 21: 2026-05-21
10 | 7 |  | PO609900 | 50W | 1000 | Qty | 2026-04-01 17: 1000 |  | 10
[6 empty] | Date | 2026-04-01 17: 2026-04-17
11 | 8 |  | PO609915 | 35W | 2000 | Qty | 2026-04-01 18: 2000 |  | 11
[6 empty] | Date | 2026-04-01 18: 2026-04-25
|  |  |  | 30W 3 Diode | 5 | Qty | Mar-26 12: 5
[6 empty] | Date | Mar-26 12: TBD
12 | 9 |  | PO609926 | 50W | 2000 | Qty | 2026-05-01 19: 720; 2026-05-01 20: 1280 |  | 12
[6 empty] | Date | 2026-05-01 19: 2026-05-02; 2026-05-01 20: 2026-05-08
13 | 10 |  | PO609945 | 50W | 1000 | Qty | 2026-05-01 20: 1000 |  | 13
[6 empty] | Date | 2026-05-01 20: 2026-05-12
16900 |  | Salary Payment |  |  |  | Working Day | [5 empty] | Paid | Paid | 3 | 5 | 6 | 6 | 2 |  | 4 | 4 | 5 | 6 | 6 | 6 | 6 | 6 |  | 65
[6 empty] | Cost | [7 empty] | 3195.2663 | 5520.8873 | 6625.0647 | 6625.0647 | 2208.3549 |  | 4416.7098 | 4416.7098 | 5520.8873 | 6625.0647 | 6625.0647 | 6625.0647 | 6625.0647 | 6625.0647 | 0 | 71654.2685
| Schedule |  |  | Status | Oct |  | 2026-01-01 3: Nov; 2026-04-01 17: Nov; 2026-05-01 21: Nov
[5 empty] | W1 |  | W3 | W4 | W1 | W1 |  | W3 | W4 | [7 empty] | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2
J-Leaf 295 Wp (1,500 pcs)
|  | Material Procurement |  | TBC
|  | Delivery Raw Material |  | 17 | [9 empty] | #REF! | bar: Nov W1 to Nov W2; Nov W1 to Nov W2
|  | Production |  | TBC
|  | Delivery to CMWI | [5 empty] | 150 | 540 | 540 |  | 390 | 420 | [7 empty] | W4: 150; Nov W1: 540; Nov W4: 150; Nov W1: 540
Feb 10th Schedule
Internal No | No. | Company | PO | Panel | PO Qty | Month | 2026-01-01 |  |  |  |  | Feb-26 |  |  |  | Mar-26 |  |  |  |  | W3: 2026-04-01; Nov W3: 2026-05-01
[6 empty] | Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
5 | 1 | Valterra | PO609684 | 50W | 1000 | Qty | Feb-26 7: 540; Feb-26 8: 460; Mar-26 13: Eid Al-Fitr Holiday |  | 5
[6 empty] | Date | Feb-26 7: 2nd Week; Feb-26 8: 3rd Week |  |  | 150 | 2025-10-31
6 | 2 |  | PO609804 | 35W | 1000 | Qty | 2026-01-01 3: 30; 2026-01-01 4: 90; Feb-26 6: 420; Feb-26 7: 450; Feb-26 8: 10 |  | 6
[6 empty] | Date | 2026-01-01 3: 16 Jan; 2026-01-01 4: 24 Jan; Feb-26 6: 5 Feb; Feb-26 7: 2nd Week; Feb-26 8: 3rd Week
7 | 3 |  | PO609784 | 50W | 1000 | Qty | Feb-26 9: 720; Mar-26 10: 280 |  | 7
[6 empty] | Date | Feb-26 9: End Feb; Mar-26 10: 1st Week
8 | 4 |  | PO609820 | 35W | 4000 | Qty | Feb-26 8: 500; Mar-26 11: 1260; Mar-26 14: 240; 2026-04-01 15: 2000 |  | 8
[6 empty] | Date | Feb-26 8: 3rd Week; Mar-26 11: 2nd Week; Mar-26 14: End Mar; 2026-04-01 15: 1st Week
9 | 5 |  | PO609880 | 50W | 1000 | Qty | Mar-26 14: 1000 |  | 9
[6 empty] | Date | Mar-26 14: End Mar
4 | 6 |  | PO609614 | 110W | 1500 | Qty | 2026-04-01 16: 1500 |  | 4
[6 empty] | Date | 2026-04-01 16: 2nd Week
10 | 7 |  | PO609900 | 50W | 1000 | Qty | 2026-04-01 17: 1000 |  | 10
[6 empty] | Date | 2026-04-01 17: 3rd Week
11 | 8 |  | PO609915 | 35W | 2000 | Qty | 2026-04-01 18: 2000 |  | 11
[6 empty] | Date | 2026-04-01 18: End Apr
|  |  |  | 30W 3 Diode | 5 | Qty | Mar-26 10: 5
[6 empty] | Date | Mar-26 10: 1st Week
12 | 9 |  | PO609926 | 50W | 2000 | Qty | 2026-05-01 19: 2000 |  | 12
[6 empty] | Date | 2026-05-01 19: 1st Week
13 | 10 |  | PO609945 | 50W | 1000 | Qty | 2026-05-01 20: 1000 |  | 13
[6 empty] | Date | 2026-05-01 20: 2nd Week
Feb 4th Schedule
| No. | Company | PO | Panel | PO Qty | Month | 2026-01-01 1: 2026-01-01; Feb-26 6: Feb-26; Mar-26 10: Mar-26; 2026-04-01 15: 2026-04-01; 2026-05-01 19: 2026-04-01
[6 empty] | Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 15 | 16 | 17 | 18
| 1 | Valterra | PO609684 | 50W | 1000 | Qty | Feb-26 7: 1000; Mar-26 13: Eid Al-Fitr Holiday
[6 empty] | Date | Feb-26 7: 2nd Week
| 2 |  | PO609804 | 35W | 1000 | Qty | 2026-01-01 3: 30; 2026-01-01 4: 90; Feb-26 6: 420; Feb-26 7: 460
[6 empty] | Date | 2026-01-01 3: 16 Jan; 2026-01-01 4: 24 Jan; Feb-26 6: 1st Week; Feb-26 7: 2nd Week
| 3 |  | PO609784 | 50W | 1000 | Qty | Feb-26 8: 1000
[6 empty] | Date | Feb-26 8: 3rd Week
| 4 |  | PO609820 | 35W | 4000 | Qty | Feb-26 8: 680; Feb-26 9: 1320; Mar-26 10: 540; Mar-26 11: 1460
[6 empty] | Date | Feb-26 8: 3rd Week; Feb-26 9: End Feb; Mar-26 10: 1st Week; Mar-26 11: 2nd Week
| 5 |  | PO609880 | 50W | 1000 | Qty | Feb-26 9: 180; Mar-26 10: 820
[6 empty] | Date | Feb-26 9: End Feb; Mar-26 10: 1st Week
| 6 |  | PO609614 | 110W | 1500 | Qty | Mar-26 12: 720; Mar-26 14: 780
[6 empty] | Date | Mar-26 12: 3rd Week; Mar-26 14: End Mar
| 7 |  | PO609900 | 50W | 1000 | Qty | 2026-04-01 15: 500; 2026-04-01 16: 500; 2026-04-01 15: 500; 2026-04-01 16: 500
[6 empty] | Date | 2026-04-01 15: 1st Week; 2026-04-01 16: 2nd Week; 2026-04-01 15: 1st Week; 2026-04-01 16: 2nd Week
| 8 |  | PO609915 | 35W | 2000 | Qty | 2026-04-01 16: 1000; 2026-04-01 17: 1000; 2026-04-01 16: 1000; 2026-04-01 17: 1000
[6 empty] | Date | 2026-04-01 16: 2nd Week; 2026-04-01 17: 3rd Week; 2026-04-01 16: 2nd Week; 2026-04-01 17: 3rd Week
|  |  |  | 30W 3 Diode | 5 | Qty | Feb-26 8: 5
[6 empty] | Date | Feb-26 8: 3rd Week
| 9 |  | PO609926 | 50W | 2000 | Qty | 2026-04-01 17: 1000; 2026-04-01 18: 1000; 2026-04-01 17: 1000; 2026-04-01 18: 1000
[6 empty] | Date | 2026-04-01 17: 3rd Week; 2026-04-01 18: End Apr; 2026-04-01 17: 3rd Week; 2026-04-01 18: End Apr
| 10 |  | PO609945 | 50W | 1000 | Qty | 2026-04-01 18: 1000; 2026-04-01 18: 1000
[6 empty] | Date | 2026-04-01 18: End Apr; 2026-04-01 18: End Apr
[7 empty] | 2026-04-01 18: Total IDR : | 1210957138
Update, 10 March 2026
Internal No | No. | Company | PO | Panel | PO Qty | Month | 2026-01-01 1: 2026-01-01; Feb-26 6: Feb-26; Mar-26 10: Mar-26; 2026-04-01 15: 2026-04-01
[6 empty] | Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
5 | 1 | Valterra | PO609684 | 50W | 1000 | Qty | Feb-26 7: 540; Feb-26 8: 420; Mar-26 11: 40 |  | 5
[6 empty] | Date | Feb-26 7: 14 Feb; Feb-26 8: 21 Feb; Mar-26 11: 2026-03-11 |  |  | 150 | 2025-10-31
6 | 2 |  | PO609804 | 35W | 1000 | Qty | 2026-01-01 3: 30; 2026-01-01 4: 90; Feb-26 6: 420; Feb-26 7: 450; Feb-26 8: 10 |  | 6
[6 empty] | Date | 2026-01-01 3: 16 Jan; 2026-01-01 4: 24 Jan; Feb-26 6: 5 Feb; Feb-26 7: 13 Feb; Feb-26 8: 21 Feb
7 | 3 |  | PO609784 | 50W | 1000 | Qty | Mar-26 11: 140; Mar-26 12: 540; Mar-26 14: 320 |  | 7
[6 empty] | Date | Mar-26 11: 2026-03-11; Mar-26 12: 2026-03-16; Mar-26 14: 2026-03-27
8 | 4 |  | PO609820 | 35W | 4000 | Qty | Feb-26 8: 320; Mar-26 10: 180; Mar-26 11: 540; Mar-26 12: 900; Mar-26 14: 540; 2026-04-01 15: 720; 2026-04-01 16: 800 |  | 8
[6 empty] | Date | Feb-26 8: 21 Feb; Mar-26 10: 2026-03-07; Mar-26 11: 2026-03-11; Mar-26 12: 2026-03-16; Mar-26 14: 2026-03-27; 2026-04-01 15: 2026-04-03; 2026-04-01 16: 2026-04-09
9 | 5 |  | PO609880 | 50W | 1000 | Qty | 2026-04-01 16: 1000 |  | 9
[6 empty] | Date | 2026-04-01 16: 2026-04-11
4 | 6 |  | PO609614 | 110W | 1500 | Qty | 2026-04-01 21: 1000 |  | 4
[6 empty] | Date | 2026-04-01 21: 2026-05-21
10 | 7 |  | PO609900 | 50W | 1000 | Qty | 2026-04-01 17: 1000 |  | 10
[6 empty] | Date | 2026-04-01 17: 2026-04-17
11 | 8 |  | PO609915 | 35W | 2000 | Qty | 2026-04-01 18: 2000 |  | 11
[6 empty] | Date | 2026-04-01 18: 2026-04-25
|  |  |  | 30W 3 Diode | 5 | Qty | Mar-26 12: 5
[6 empty] | Date | Mar-26 12: TBD
12 | 9 |  | PO609926 | 50W | 2000 | Qty | 2026-04-01 19: 720; 2026-04-01 20: 1280 |  | 12
[6 empty] | Date | 2026-04-01 19: 2026-05-02; 2026-04-01 20: 2026-05-08
13 | 10 |  | PO609945 | 50W | 1000 | Qty | 2026-04-01 20: 1000 |  | 13
[6 empty] | Date | 2026-04-01 20: 2026-05-12

## Schedule Production (1) (hidden)
February 2026
MASTER PLANNING SCHEDULE
|  |  | Idle : | 7 |  | Normal Days : | 20 | Working Days : | 13 |  | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
No | No PO | Customers | Detailed Product |  |  | Qty (Order) | Production Process |  |  | Total Plan | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
|  |  | Type | Label | Wp | [5 empty] | M 9: 2; T 10: 2; W 11: 2; T 12: 2; F 13: 2; S 14: 2; M 16: 2; T 17: 2; W 18: 2; T 19: 2; F 20: 1; T 26: 2; F 27: 2; S 28: 2
1 | 00609804 (No.6) | VALTERRA | 73907-F | THERMOKING | 35 | 1000 | Prepration - Cutting Laser Module |  |  | 450 | F 6: 150; M 9: 160; T 10: 140
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 460 | M 9: 240; T 10: 220
2 | 00609684 (No.5) | VALTERRA | 82882-C | NAVIGATOR | 50 | 1000 | Prepration - Cutting Laser Module |  |  | 1000 | T 10: 80; W 11: 240; T 12: 240; F 13: 240; S 14: 200
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 960 | T 10: 60; W 11: 240; T 12: 240; F 13: 240; S 14: 180
4 | 00609820 (Part 1) (No.8) | VALTERRA | 73907-F | THERMOKING | 35 | 500 | Prepration - Cutting Laser Module |  |  | 500 | W 18: 180; T 19: 240; F 20: 80
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 320 | W 18: 60; T 19: 140; F 20: 120
5. | 00609820 (Part 2) (No.8) | VALTERRA | 73907-F | THERMOKING | 35 | 1500 | Prepration - Cutting Laser Module |  |  | 0 | bar: S 15 to T 17
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 0 | bar: S 15 to T 17
5 | 00609880 | VALTERRA | 82882-C | THERMOKING | 50 | 1000 | Prepration - Cutting Laser Module |  |  | 0
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 0
[7 empty] | Prepration - Cutting Laser Module |  |  | 1950 | T 12: 35W (PO.9804); M 16: 50W (PO.9684); F 20: 35W (PO.9804 & 9820); W 25: 35W (PO.9820)
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 1740 | F 13: 450 PCS (US); T 17: 540 pcs (IRE); F 20: 10 + 320 PCS (US); T 26: 180 PCS; S 28: (US)
50W (PO.9684)
|  | March 2026 | [8 empty] | S 21: 420 pcs; M 23: (IRE)
MASTER PLANNING SCHEDULE
|  |  | Idle : | 1 |  | Normal Days : | 19 | Working Days : | 18 |  | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T
No | No PO | Customers | Detailed Product |  |  | Qty (Order) | Production Process |  |  | Total Plan | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
|  |  | Type | Label | Wp | [5 empty] | W 4: 2; T 5: 2; F 6: 2; S 7: 2; M 9: 2; T 10: 2; W 11: 2; T 12: 2; F 13: 2; S 14: 2; M 16: 2; T 17: 2; W 25: 2; T 26: 2; F 27: 2; S 28: 2; M 30: 2; T 31: 2
1 | 00609684 (No.5) | VALTERRA | 82882-C | NAVIGATOR | 50 | 1000 | Prepration - Cutting Laser Module |  |  | 0 | bar: W 18 to T 24
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 40 | W 4: 40
2 | 00609820 (Part 1) (No.8) | VALTERRA | 73907-F | THERMOKING | 35 | 500 | Prepration - Cutting Laser Module |  |  | 0 | bar: W 18 to T 24
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 180 | W 4: 180
3 | 00609820 (Part 2) (No.8) | VALTERRA | 73907-F | THERMOKING | 35 | 1500 | Prepration - Cutting Laser Module |  |  | 1500 | W 4: 140; T 5: 180; F 6: 220; M 9: 200; T 10: 240; W 11: 240; T 12: 160; F 13: 120
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 1500 | W 4: 140; T 5: 180; F 6: 220; F 13: 140; S 14: 180; S 15: 220; M 16: 240; T 17: 180
4 | 00609784 (No.7) | VALTERRA | 82882-C | NAVIGATOR | 50 | 1000 | Prepration - Cutting Laser Module |  |  | 1000 | S 7: 140; F 13: 100; S 14: 240; S 15: 240; M 16: 200; T 17: 80
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 1000 | S 7: 140; T 17: 20; W 25: 120; T 26: 240; F 27: 240; S 28: 240
5 | 00609820 (Part 3) (No.8) | VALTERRA | 73907 - F | THERMOKING | 35 | 2000 | Prepration - Cutting Laser Module |  |  | 1500 | T 17: 60; W 25: 160; T 26: 160; F 27: 280; S 28: 280; M 30: 280; T 31: 280
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 460 | M 30: 180; T 31: 280
[7 empty] | Prepration - Cutting Laser Module |  |  | 2500
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 2720
April 2026
MASTER PLANNING SCHEDULE
|  |  | Idle : | -4 |  | Normal Days : | 19 | Working Days : | 23 |  | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T
No | No PO | Customers | Detailed Product |  |  | Qty (Order) | Production Process |  |  | Total Plan | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
|  |  | Type | Label | Wp | [5 empty] | 2 | 2 |  |  |  |  | 2 | 2 | 2 | 2 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 |  | 2 | 2 | 2 | 2
1 | 00609820 (Part 3) (No.8) | VALTERRA | 73907 - F | THERMOKING | 35 | 2000 | Prepration - Cutting Laser Module |  |  | 620 | W 1: 280; T 2: 280; T 7: 60
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 1540 | W 1: 280; T 2: 280; T 7: 280; W 8: 280; T 9: 280; F 10: 140
2 | 00609614 (No.4) | VALTERRA | 83060-B | DOMETIC | 110 | 1500 | Prepration - Cutting Laser Module |  |  | 1500 | M 13: 120; T 14: 180; W 15: 240; T 16: 240; F 17: 240; S 18: 240; M 20: 240
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 1500 | T 16: 180; F 17: 240; S 18: 240; M 20: 240; T 21: 240; W 22: 240; T 23: 120
3 | 00609880 (No.9) | VALTERRA | 82882-C | THERMOKING | 50 | 1000 | Prepration - Cutting Laser Module |  |  | 1000 | T 7: 120; W 8: 160; T 9: 240; F 10: 240; S 11: 240
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 1000 | F 10: 80; S 11: 160; M 13: 240; T 14: 240; W 15: 240; T 16: 40
4 | 00609900 | VALTERRA | 73907 - F | THERMOKING | 50 | 1000 | Prepration - Cutting Laser Module |  |  | 1000 | T 21: 120; W 22: 180; T 23: 240; F 24: 240; S 25: 220
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 1000 | F 24: 80; S 25: 160; M 27: 240; T 28: 240; W 29: 240; T 30: 40
5 | 00609915 | VALTERRA | 82882-C | THERMOKING | 35 | 2000 | Prepration - Cutting Laser Module |  |  | 980 | M 27: 180; T 28: 240; W 29: 280; T 30: 280
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 0 | bar: F 3 to M 6
[7 empty] | Prepration - Cutting Laser Module |  |  | 5100
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 5040
May 2026
MASTER PLANNING SCHEDULE
|  |  | Idle : | 0 |  | Normal Days : | 19 | Working Days : | 19 |  | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
No | No PO | Customers | Detailed Product |  |  | Qty (Order) | Production Process |  |  | Total Plan | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
|  |  | Type | Label | Wp | [5 empty] | 2 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 |  | 2 | 2 | 2 | 2 | 2
1 | 00609915 | VALTERRA | 82882-C | THERMOKING | 35 | 2000 | Prepration - Cutting Laser Module |  |  | 1020 | F 1: 240; S 2: 240; M 4: 240; T 5: 280; W 6: 20
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 2000 | F 1: 180; S 2: 280; M 4: 280; T 5: 280; W 6: 280; T 7: 280; F 8: 240; S 9: 180
2 | 00609926 | VALTERRA | 82882-C | THERMOKING | 50 | 2000 | Prepration - Cutting Laser Module |  |  | 2000 | W 6: 180; T 7: 240; F 8: 240; M 11: 240; T 12: 240; W 13: 240; T 14: 240; F 15: 240; S 16: 140
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 2000 | T 7: 180; F 8: 240; M 11: 240; T 12: 240; W 13: 240; T 14: 240; F 15: 240; S 16: 240; M 18: 140
3 | 00609945 | VALTERRA | 82882-C | THERMOKING | 50 | 1000 | Prepration - Cutting Laser Module |  |  | 1000 | S 16: 60; M 18: 240; T 19: 240; W 20: 240; T 21: 220
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 1000 | M 18: 60; T 19: 240; W 20: 240; T 21: 240; F 22: 220
[7 empty] | Prepration - Cutting Laser Module |  |  | 4020
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 5000
Estimated Arrival J-Box Material
DONE
DONE
DONE
DONE
Note on U8: Yutio Sapnanda: WIP w/o J-Box
Note on X8: Yutio Sapnanda: Incoming Check, Instalation J-Box & Packing Box
Note on Y8: Yutio Sapnanda: Shift 1 Finish
Note on Y10: Yutio Sapnanda: Shift 2
Note on AP29: "Al Isra Wal Miraj Prophet Mohammad SAW's Miraculous Journey".
Note on AR29: Chinese New Year

## Schedule Production (2) (hidden)
February 2026
MASTER PLANNING SCHEDULE
|  |  | Idle : | 7 |  | Normal Days : | 20 | Working Days : | 13 |  | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
No | No PO | Customers | Detailed Product |  |  | Qty (Order) | Production Process |  |  | Total Plan | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
|  |  | Type | Label | Wp | [5 empty] | M 9: 2; T 10: 2; W 11: 2; T 12: 2; F 13: 2; S 14: 2; M 16: 2; T 17: 2; W 18: 2; T 19: 2; F 20: 1; T 26: 2; F 27: 2; S 28: 2
1 | 00609804 (No.6) | VALTERRA | 73907-F | THERMOKING | 35 | 1000 | Prepration - Cutting Laser Module |  |  | 450 | F 6: 150; M 9: 160; T 10: 140
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 460 | M 9: 240; T 10: 220
2 | 00609684 (No.5) | VALTERRA | 82882-C | NAVIGATOR | 50 | 1000 | Prepration - Cutting Laser Module |  |  | 1000 | T 10: 80; W 11: 240; T 12: 240; F 13: 240; S 14: 200
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 960 | T 10: 60; W 11: 240; T 12: 240; F 13: 240; S 14: 180
4 | 00609820 (Part 1) (No.8) | VALTERRA | 73907-F | THERMOKING | 35 | 500 | Prepration - Cutting Laser Module |  |  | 500 | W 18: 180; T 19: 240; F 20: 80
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 320 | W 18: 60; T 19: 140; F 20: 120
5. | 00609820 (Part 2) (No.8) | VALTERRA | 73907-F | THERMOKING | 35 | 1500 | Prepration - Cutting Laser Module |  |  | 0 | bar: S 15 to T 17
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 0 | bar: S 15 to T 17
5 | 00609880 | VALTERRA | 82882-C | THERMOKING | 50 | 1000 | Prepration - Cutting Laser Module |  |  | 0
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 0
[7 empty] | Prepration - Cutting Laser Module |  |  | 1950 | T 12: 35W (PO.9804); M 16: 50W (PO.9684); F 20: 35W (PO.9804 & 9820); W 25: 35W (PO.9820)
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 1740 | F 13: 450 PCS (US); T 17: 540 pcs (IRE); F 20: 10 + 320 PCS (US); T 26: 180 PCS; S 28: (US)
50W (PO.9684)
|  | March 2026 | [8 empty] | S 21: 420 pcs; M 23: (IRE)
MASTER PLANNING SCHEDULE
|  |  | Idle : | 0 |  | Normal Days : | 19 | Working Days : | 19 |  | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T
No | No PO | Customers | Detailed Product |  |  | Qty (Order) | Production Process |  |  | Total Plan | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
|  |  | Type | Label | Wp | [9 empty] | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | [7 empty] | 2 | 2 | 2 | 2 |  | 2 | 2
1 | 00609684 (No.5) | VALTERRA | 82882-C | NAVIGATOR | 50 | 1000 | Prepration - Cutting Laser Module |  |  | 0 | bar: W 18 to T 24
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 40 | T 5: 40
2 | 00609820 (Part 1) (No.8) | VALTERRA | 73907-F | THERMOKING | 35 | 500 | Prepration - Cutting Laser Module |  |  | 0 | bar: W 18 to T 24
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 180 | T 5: 180
3 | 00609820 (Part 2) (No.8) | VALTERRA | 73907-F | THERMOKING | 35 | 1500 | Prepration - Cutting Laser Module |  |  | 1500 | F 6: 160; S 7: 220; S 8: 280; M 9: 280; T 10: 80; W 11: 280; T 12: 200
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 1500 | F 6: 80; S 7: 140; S 8: 240; M 9: 80; S 14: 600; S 15: 300; M 16: 60
4 | 00609784 (No.7) | VALTERRA | 82882-C | NAVIGATOR | 50 | 1000 | Prepration - Cutting Laser Module |  |  | 1000 | T 10: 140; F 13: 240; S 14: 160; M 16: 240; T 17: 120; W 25: 100
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 1000 | T 10: 140; S 15: 400; M 16: 140; T 17: 160; W 25: 160
5 | 00609820 (Part 3) (No.8) | VALTERRA | 73907 - F | THERMOKING | 35 | 2000 | Prepration - Cutting Laser Module |  |  | 1360 | T 26: 240; F 27: 280; S 28: 280; M 30: 280; T 31: 280
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 1360 | T 26: 240; F 27: 280; S 28: 280; M 30: 280; T 31: 280
[7 empty] | Prepration - Cutting Laser Module |  |  | 2500 | S 7: 35W (PO.9820); T 10: 35W (PO.9820); F 13: 50W (PO.9684 & 9784); T 17: 35W PO.9820; F 27: 35W (PO.9820); M 30: 35W (PO.9820)
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 2720 | S 7: 180 pcs; T 10: 540 PCS; F 13: 40 + 140 PCS; T 17: 900 pcs; F 27: 540; M 30: 920
50W PO.9784
|  | April 2026 | [8 empty] | T 17: 540 pcs
MASTER PLANNING SCHEDULE
|  |  | Idle : | -4 |  | Normal Days : | 19 | Working Days : | 23 |  | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T
No | No PO | Customers | Detailed Product |  |  | Qty (Order) | Production Process |  |  | Total Plan | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
|  |  | Type | Label | Wp | [5 empty] | 2 | 2 |  |  |  |  | 2 | 2 | 2 | 2 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 |  | 2 | 2 | 2 | 2
1 | 00609784 (No.7) | VALTERRA | 82882-C | NAVIGATOR | 50 | 1000 | Prepration - Cutting Laser Module |  |  | 640 | W 1: 280; T 2: 280; T 7: 80
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 640 | W 1: 280; T 2: 280; T 7: 80
3 | 00609880 (No.9) | VALTERRA | 82882-C | THERMOKING | 50 | 1000 | Prepration - Cutting Laser Module |  |  | 1000 | T 7: 80; W 8: 240; T 9: 240; F 10: 240; S 11: 200
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 1000 | T 7: 40; W 8: 240; T 9: 240; F 10: 240; S 11: 240
4 | 00609900 | VALTERRA | 73907 - F | THERMOKING | 50 | 1000 | Prepration - Cutting Laser Module |  |  | 1000 | M 13: 160; T 14: 240; W 15: 240; T 16: 240; F 17: 120
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 1000 | M 13: 160; T 14: 240; W 15: 240; T 16: 240; F 17: 120
5 | 00609915 | VALTERRA | 82882-C | THERMOKING | 35 | 2000 | Prepration - Cutting Laser Module |  |  | 2000 | F 17: 120; S 18: 280; M 20: 280; T 21: 280; W 22: 280; T 23: 280; F 24: 280; S 25: 200
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 2000 | F 17: 80; S 18: 240; M 20: 280; T 21: 280; W 22: 280; T 23: 280; F 24: 280; S 25: 280
6 | 00609926 | VALTERRA | 82882-C | THERMOKING | 50 | 2000 | Prepration - Cutting Laser Module |  |  | 1040 | M 27: 200; T 28: 280; W 29: 280; T 30: 280
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 920 | M 27: 80; T 28: 280; W 29: 280; T 30: 280
[7 empty] | Prepration - Cutting Laser Module |  |  | 4640
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 4640
May 2026
MASTER PLANNING SCHEDULE
|  |  | Idle : | 3 |  | Normal Days : | 19 | Working Days : | 16 |  | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
No | No PO | Customers | Detailed Product |  |  | Qty (Order) | Production Process |  |  | Total Plan | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
|  |  | Type | Label | Wp | [5 empty] | F 1: 2; S 2: 2; M 4: 2; T 5: 2; W 6: 2; T 7: 2; F 8: 2; S 9: 2; M 11: 2; T 12: 2; W 13: 2; T 14: 2; F 15: 2; S 16: 2; M 18: 2; T 19: 2
1 | 00609926 | VALTERRA | 82882-C | THERMOKING | 50 | 2000 | Prepration - Cutting Laser Module |  |  | 960 | F 1: 240; S 2: 240; M 4: 240; T 5: 240
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 1080 | F 1: 240; S 2: 240; M 4: 240; T 5: 240; W 6: 120
2 | 00609945 | VALTERRA | 82882-C | THERMOKING | 50 | 1000 | Prepration - Cutting Laser Module |  |  | 1000 | W 6: 240; T 7: 240; F 8: 240; S 9: 240; M 11: 40
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 1000 | W 6: 80; T 7: 240; F 8: 240; S 9: 240; M 11: 200
3 | 00609914 | VALTERRA | 0 | THERMOKING | 110 | 1500 | Prepration - Cutting Laser Module |  |  | 1500 | M 11: 160; T 12: 240; W 13: 240; T 14: 240; F 15: 240; S 16: 240; M 18: 140
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 1500 | T 12: 240; W 13: 240; T 14: 240; F 15: 240; S 16: 240; M 18: 240; T 19: 60
[7 empty] | Prepration - Cutting Laser Module |  |  | 3460
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 3580
Estimated Arrival J-Box Material
DONE
DONE
DONE
DONE
DONE
Pick Up, 14 Mar
Pick Up, 11 Mar
Pick Up, 16 Mar (21:00)
Pick Up, 16 Mar (21:00)
Note on U8: Yutio Sapnanda: WIP w/o J-Box
Note on X8: Yutio Sapnanda: Incoming Check, Instalation J-Box & Packing Box
Note on Y8: Yutio Sapnanda: Shift 1 Finish
Note on Y10: Yutio Sapnanda: Shift 2
Note on AP29: "Al Isra Wal Miraj Prophet Mohammad SAW's Miraculous Journey".
Note on AR29: Chinese New Year

## Schedule Production (Original)
February 2026
MASTER PLANNING SCHEDULE
|  |  | Idle : | 7 |  | Normal Days : | 20 | Working Days : | 13 |  | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
No | No PO | Customers | Detailed Product |  |  | Qty (Order) | Production Process |  |  | Total Plan | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
|  |  | Type | Label | Wp | [5 empty] | M 9: 2; T 10: 2; W 11: 2; T 12: 2; F 13: 2; S 14: 2; M 16: 2; T 17: 2; W 18: 2; T 19: 2; F 20: 1; T 26: 2; F 27: 2; S 28: 2
1 | 00609804 (No.6) | VALTERRA | 73907-F | THERMOKING | 35 | 1000 | Prepration - Cutting Laser Module |  |  | 450 | F 6: 150; M 9: 160; T 10: 140
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 460 | M 9: 240; T 10: 220
2 | 00609684 (No.5) | VALTERRA | 82882-C | NAVIGATOR | 50 | 1000 | Prepration - Cutting Laser Module |  |  | 1000 | T 10: 80; W 11: 240; T 12: 240; F 13: 240; S 14: 200
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 960 | T 10: 60; W 11: 240; T 12: 240; F 13: 240; S 14: 180
4 | 00609820 (Part 1) (No.8) | VALTERRA | 73907-F | THERMOKING | 35 | 500 | Prepration - Cutting Laser Module |  |  | 500 | W 18: 180; T 19: 240; F 20: 80
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 320 | W 18: 60; T 19: 140; F 20: 120
5. | 00609820 (Part 2) (No.8) | VALTERRA | 73907-F | THERMOKING | 35 | 1500 | Prepration - Cutting Laser Module |  |  | 0 | bar: S 15 to T 17
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 0 | bar: S 15 to T 17
5 | 00609880 | VALTERRA | 82882-C | THERMOKING | 50 | 1000 | Prepration - Cutting Laser Module |  |  | 0
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 0
[7 empty] | Prepration - Cutting Laser Module |  |  | 1950 | T 12: 35W (PO.9804); M 16: 50W (PO.9684); F 20: 35W (PO.9804 & 9820); W 25: 35W (PO.9820)
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 1740 | F 13: 450 PCS (US); T 17: 540 pcs (IRE); F 20: 10 + 320 PCS (US); T 26: 180 PCS; S 28: (US)
50W (PO.9684)
|  | March 2026 | [8 empty] | S 21: 420 pcs; M 23: (IRE)
MASTER PLANNING SCHEDULE
|  |  | Idle : | 1 |  | Normal Days : | 19 | Working Days : | 18 |  | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T
No | No PO | Customers | Detailed Product |  |  | Qty (Order) | Production Process |  |  | Total Plan | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
|  |  | Type | Label | Wp | [5 empty] | T 5: 1; F 6: 2; S 7: 2; S 8: 2; M 9: 2; T 10: 2; W 11: 2; T 12: 2; F 13: 2; S 14: 2; S 15: 2; M 16: 1; W 25: 2; T 26: 2; F 27: 2; S 28: 2; M 30: 2; T 31: 2
1 | 00609684 (No.5) | VALTERRA | 82882-C | NAVIGATOR | 50 | 1000 | Prepration - Cutting Laser Module |  |  | 0 | bar: W 18 to T 24
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 40 | T 5: 40
2 | 00609820 (Part 1) (No.8) | VALTERRA | 73907-F | THERMOKING | 35 | 500 | Prepration - Cutting Laser Module |  |  | 0 | bar: W 18 to T 24
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 180 | T 5: 180
3 | 00609820 (Part 2) (No.8) | VALTERRA | 73907-F | THERMOKING | 35 | 1500 | Prepration - Cutting Laser Module |  |  | 1500 | S 7: 240; S 8: 300; M 9: 140; T 10: 300; W 11: 300; T 12: 220
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 1500 | S 7: 240; S 8: 300; S 14: 400; S 15: 500; W 25: 60
4 | 00609784 (No.7) | VALTERRA | 82882-C | NAVIGATOR | 50 | 1000 | Prepration - Cutting Laser Module |  |  | 1000 | M 9: 140; F 13: 240; S 14: 120; W 25: 200; T 26: 240; F 27: 60
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 1000 | M 9: 140; S 15: 360; W 25: 80; T 26: 280; F 27: 140
5 | 00609820 (Part 3) (No.8) | VALTERRA | 73907 - F | THERMOKING | 35 | 2000 | Prepration - Cutting Laser Module |  |  | 1240 | M 16: 120; F 27: 280; S 28: 280; M 30: 280; T 31: 280
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 1060 | M 16: 80; F 27: 140; S 28: 280; M 30: 280; T 31: 280
[7 empty] | Prepration - Cutting Laser Module |  |  | 2500 | S 7: 35W (PO.9820); T 10: 35W (PO.9820); F 13: 50W (PO.9684 & 9784); T 17: 35W PO.9820; F 27: 35W (PO.9820); M 30: 50W (PO.9784)
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 2720 | S 7: 180 pcs; T 10: 540 PCS; F 13: 40 + 140 PCS; T 17: 900 pcs; F 27: 540; M 30: 500
50W PO.9784
|  | April 2026 | [7 empty] | 2000 | T 17: 360 pcs
|  | MASTER PLANNING SCHEDULE | [7 empty] | 2000
|  |  | Idle : | -4 |  | Normal Days : | 19 | Working Days : | 23 |  | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T
No | No PO | Customers | Detailed Product |  |  | Qty (Order) | Production Process |  |  | Total Plan | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
|  |  | Type | Label | Wp | [5 empty] | 2 | 2 |  |  |  |  | 2 | 2 | 2 | 2 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 |  | 2 | 2 | 2 | 2
1 | 00609820 (Part 3) (No.8) | VALTERRA | 73907-F | THERMOKING | 35 | 2000 | Prepration - Cutting Laser Module |  |  | 760 | W 1: 280; T 2: 280; T 7: 200
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 940 | W 1: 280; T 2: 280; T 7: 280; W 8: 100
3 | 00609880 (No.9) | VALTERRA | 82882-C | THERMOKING | 50 | 1000 | Prepration - Cutting Laser Module |  |  | 1000 | T 7: 80; W 8: 240; T 9: 240; F 10: 240; S 11: 200
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 1000 | W 8: 140; T 9: 240; F 10: 240; S 11: 240; M 13: 140
4 | 00609900 | VALTERRA | 73907 - F | THERMOKING | 50 | 1000 | Prepration - Cutting Laser Module |  |  | 1000 | M 13: 160; T 14: 240; W 15: 240; T 16: 240; F 17: 120
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 1000 | M 13: 80; T 14: 240; W 15: 240; T 16: 240; F 17: 200
5 | 00609915 | VALTERRA | 82882-C | THERMOKING | 35 | 2000 | Prepration - Cutting Laser Module |  |  | 2000 | F 17: 120; S 18: 280; M 20: 280; T 21: 280; W 22: 280; T 23: 280; F 24: 280; S 25: 200
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 2000 | F 17: 80; S 18: 240; M 20: 280; T 21: 280; W 22: 280; T 23: 280; F 24: 280; S 25: 280
6 | 00609926 | VALTERRA | 82882-C | THERMOKING | 50 | 2000 | Prepration - Cutting Laser Module |  |  | 1040 | M 27: 200; T 28: 280; W 29: 280; T 30: 280
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 920 | M 27: 80; T 28: 280; W 29: 280; T 30: 280
[7 empty] | Prepration - Cutting Laser Module |  |  | 4760 | F 3: 35W (PO.9820); T 9: 35W (PO.9820); F 17: 50W (PO.9900); S 25: 35W (PO.9915)
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 4940 | F 3: 540; T 9: 800 pcs; F 17: 1000 PCS; S 25: 2000 PCS
|  | May 2026 | [8 empty] | T 9: 50W (PO.9880)
|  | MASTER PLANNING SCHEDULE | [8 empty] | T 9: 1000 pcs
|  |  | Idle : | 3 |  | Normal Days : | 19 | Working Days : | 16 |  | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
No | No PO | Customers | Detailed Product |  |  | Qty (Order) | Production Process |  |  | Total Plan | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
|  |  | Type | Label | Wp | [5 empty] | F 1: 2; S 2: 2; M 4: 2; T 5: 2; W 6: 2; T 7: 2; F 8: 2; 1000 pcs S 9: 2; 1000 pcs M 11: 2; 1000 pcs T 12: 2; 1000 pcs W 13: 2; 1000 pcs T 14: 2; 1000 pcs F 15: 2; 1000 pcs S 16: 2; 1000 pcs M 18: 2; 1000 pcs T 19: 2
1 | 00609926 | VALTERRA | 82882-C | THERMOKING | 50 | 2000 | Prepration - Cutting Laser Module |  |  | 960 | F 1: 240; S 2: 240; M 4: 240; T 5: 240
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 1080 | F 1: 240; S 2: 240; M 4: 240; T 5: 240; W 6: 120
2 | 00609945 | VALTERRA | 82882-C | THERMOKING | 50 | 1000 | Prepration - Cutting Laser Module |  |  | 1000 | W 6: 240; T 7: 240; F 8: 240; 1000 pcs S 9: 240; 1000 pcs M 11: 40
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 1000 | W 6: 80; T 7: 240; F 8: 240; 1000 pcs S 9: 240; 1000 pcs M 11: 200
3 | 00609914 | VALTERRA | 0 | THERMOKING | 110 | 1500 | Prepration - Cutting Laser Module |  |  | 1500 | 1000 pcs M 11: 160; 1000 pcs T 12: 240; 1000 pcs W 13: 240; 1000 pcs T 14: 240; 1000 pcs F 15: 240; 1000 pcs S 16: 240; 1000 pcs M 18: 140
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 1500 | 1000 pcs T 12: 240; 1000 pcs W 13: 240; 1000 pcs T 14: 240; 1000 pcs F 15: 240; 1000 pcs S 16: 240; 1000 pcs M 18: 240; 1000 pcs T 19: 60
[7 empty] | Prepration - Cutting Laser Module |  |  | 3460
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 3580
Preparation - Laminating = 1 Shift
Cutting Module - Packing = 2 Shift
DONE
DONE
DONE
DONE
J-BOX - Packing = 2 Shift
Arrival J-Box Material
DONE
Pick Up, 17 Mar (07:00)
Pick Up, 27 Mar
Pick Up, 27 Mar
Arrival J-Box Material
Pick Up, 17 Mar (07:00)
DONE
DONE
Pick Up, 3 Apr
Pick Up, 11 Apr
Pick Up, 9 Apr
Pick Up, 17 Apr
Pick Up, 25 Apr
Note on U8: Yutio Sapnanda: WIP w/o J-Box
Note on X8: Yutio Sapnanda: Incoming Check, Instalation J-Box & Packing Box
Note on Y8: Yutio Sapnanda: Shift 1 Finish
Note on Y10: Yutio Sapnanda: Shift 2
Note on AP29: "Al Isra Wal Miraj Prophet Mohammad SAW's Miraculous Journey".
Note on AR29: Chinese New Year

## Schedule (If EVA Delay) (hidden)
February 2026
MASTER PLANNING SCHEDULE
|  |  | Idle : | 7 |  | Normal Days : | 20 | Working Days : | 13 |  | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
No | No PO | Customers | Detailed Product |  |  | Qty (Order) | Production Process |  |  | Total Plan | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
|  |  | Type | Label | Wp | [5 empty] | M 9: 2; T 10: 2; W 11: 2; T 12: 2; F 13: 2; S 14: 2; M 16: 2; T 17: 2; W 18: 2; T 19: 2; F 20: 1; T 26: 2; F 27: 2; S 28: 2
1 | 00609804 (No.6) | VALTERRA | 73907-F | THERMOKING | 35 | 1000 | Prepration - Cutting Laser Module |  |  | 450 | F 6: 150; M 9: 160; T 10: 140
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 460 | M 9: 240; T 10: 220
2 | 00609684 (No.5) | VALTERRA | 82882-C | NAVIGATOR | 50 | 1000 | Prepration - Cutting Laser Module |  |  | 1000 | T 10: 80; W 11: 240; T 12: 240; F 13: 240; S 14: 200
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 960 | T 10: 60; W 11: 240; T 12: 240; F 13: 240; S 14: 180
4 | 00609820 (Part 1) (No.8) | VALTERRA | 73907-F | THERMOKING | 35 | 500 | Prepration - Cutting Laser Module |  |  | 500 | W 18: 180; T 19: 240; F 20: 80
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 320 | W 18: 60; T 19: 140; F 20: 120
5. | 00609820 (Part 2) (No.8) | VALTERRA | 73907-F | THERMOKING | 35 | 1500 | Prepration - Cutting Laser Module |  |  | 0 | bar: S 15 to T 17
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 0 | bar: S 15 to T 17
5 | 00609880 | VALTERRA | 82882-C | THERMOKING | 50 | 1000 | Prepration - Cutting Laser Module |  |  | 0
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 0
[7 empty] | Prepration - Cutting Laser Module |  |  | 1950 | T 12: 35W (PO.9804); M 16: 50W (PO.9684); F 20: 35W (PO.9804 & 9820); W 25: 35W (PO.9820)
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 1740 | F 13: 450 PCS (US); T 17: 540 pcs (IRE); F 20: 10 + 320 PCS (US); T 26: 180 PCS; S 28: (US)
50W (PO.9684)
|  | March 2026 | [8 empty] | S 21: 420 pcs; M 23: (IRE) | 6
MASTER PLANNING SCHEDULE
|  |  | Idle : | 1 |  | Normal Days : | 19 | Working Days : | 18 |  | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T
No | No PO | Customers | Detailed Product |  |  | Qty (Order) | Production Process |  |  | Total Plan | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
|  |  | Type | Label | Wp | [5 empty] | T 5: 1; F 6: 2; S 7: 2; S 8: 2; M 9: 2; T 10: 2; W 11: 2; T 12: 2; F 13: 2; S 14: 2; S 15: 2; M 16: 1; W 25: 2; T 26: 2; F 27: 2; S 28: 2; M 30: 2; T 31: 2
1 | 00609684 (No.5) | VALTERRA | 82882-C | NAVIGATOR | 50 | 1000 | Prepration - Cutting Laser Module |  |  | 0 | [31 empty] | Note : Delivery for 50W PO.9784 1. Pickup, Sunday 29th March & Freight 30 March 2. Pickup Monday 30th March & Freight 31 March | bar: W 18 to T 24
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 40 | T 5: 40
2 | 00609820 (Part 1) (No.8) | VALTERRA | 73907-F | THERMOKING | 35 | 500 | Prepration - Cutting Laser Module |  |  | 0 | bar: W 18 to T 24
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 180 | T 5: 180
3 | 00609820 (Part 2) (No.8) | VALTERRA | 73907-F | THERMOKING | 35 | 1500 | Prepration - Cutting Laser Module |  |  | 1500 | S 7: 240; S 8: 300; M 9: 140; T 10: 300; W 11: 300; T 12: 220
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 1500 | S 7: 240; S 8: 300; S 14: 400; S 15: 500; W 25: 60
4 | 00609784 (No.7) | VALTERRA | 82882-C | NAVIGATOR | 50 | 1000 | Prepration - Cutting Laser Module |  |  | 1000 | M 9: 140; F 13: 240; S 14: 120; M 16: 20; F 27: 240; S 28: 240
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 1000 | M 9: 140; S 15: 360; F 27: 220; S 28: 280
5 | 00609820 (Part 3) (No.8) | VALTERRA | 73907 - F | THERMOKING | 35 | 2000 | Prepration - Cutting Laser Module |  |  | 1060 | W 25: 220; T 26: 280; M 30: 280; T 31: 280
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 1040 | W 25: 180; T 26: 280; F 27: 20; M 30: 280; T 31: 280
[7 empty] | Prepration - Cutting Laser Module |  |  | 2500 | S 7: 35W (PO.9820); T 10: 35W (PO.9820); F 13: 50W (PO.9684 & 9784); T 17: 35W PO.9820; F 27: 35W (PO.9820); M 30: 50W (PO.9784)
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 2720 | S 7: 180 pcs; T 10: 540 PCS; F 13: 40 + 140 PCS; T 17: 900 pcs; F 27: 540; M 30: 500
50W PO.9784
|  | April 2026 | [7 empty] | 2000 | T 17: 360 pcs
|  | MASTER PLANNING SCHEDULE | [7 empty] | 2000
|  |  | Idle : | -4 |  | Normal Days : | 19 | Working Days : | 23 |  | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T
No | No PO | Customers | Detailed Product |  |  | Qty (Order) | Production Process |  |  | Total Plan | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
|  |  | Type | Label | Wp | [5 empty] | 2 | 2 |  |  |  |  | 2 | 2 | 2 | 2 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 |  | 2 | 2 | 2 | 2
1 | 00609820 (Part 3) (No.8) | VALTERRA | 73907 - F | THERMOKING | 35 | 2000 | Prepration - Cutting Laser Module |  |  | 940 | W 1: 280; T 2: 280; T 7: 280; W 8: 100
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 960 | W 1: 280; T 2: 280; T 7: 280; W 8: 120
3 | 00609880 (No.9) | VALTERRA | 82882-C | THERMOKING | 50 | 1000 | Prepration - Cutting Laser Module |  |  | 1000 | W 8: 40; T 9: 240; F 10: 240; S 11: 240; M 13: 240
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 1000 | T 9: 240; F 10: 240; S 11: 240; M 13: 240; T 14: 40
4 | 00609900 | VALTERRA | 73907 - F | THERMOKING | 50 | 1000 | Prepration - Cutting Laser Module |  |  | 1000 | T 14: 240; W 15: 240; T 16: 240; F 17: 240; S 18: 40
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 1000 | T 14: 200; W 15: 240; T 16: 240; F 17: 240; S 18: 80
5 | 00609915 | VALTERRA | 82882-C | THERMOKING | 35 | 2000 | Prepration - Cutting Laser Module |  |  | 2000 | S 18: 180; M 20: 280; T 21: 280; W 22: 280; T 23: 280; F 24: 280; S 25: 280; M 27: 140
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 2000 | S 18: 100; M 20: 280; T 21: 280; W 22: 280; T 23: 280; F 24: 280; S 25: 280; M 27: 220
6 | 00609926 | VALTERRA | 82882-C | THERMOKING | 50 | 2000 | Prepration - Cutting Laser Module |  |  | 800 | M 27: 80; T 28: 240; W 29: 240; T 30: 240
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 720 | T 28: 240; W 29: 240; T 30: 240
[7 empty] | Prepration - Cutting Laser Module |  |  | 4940 | F 3: 35W (PO.9820)
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 4960 | F 3: 540
|  | May 2026 | [7 empty] | 2000
|  | MASTER PLANNING SCHEDULE | [7 empty] | 2000
|  |  | Idle : | 3 |  | Normal Days : | 19 | Working Days : | 16 |  | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
No | No PO | Customers | Detailed Product |  |  | Qty (Order) | Production Process |  |  | Total Plan | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
|  |  | Type | Label | Wp | [5 empty] | F 1: 2; S 2: 2; M 4: 2; T 5: 2; W 6: 2; T 7: 2; F 8: 2; S 9: 2; M 11: 2; T 12: 2; W 13: 2; T 14: 2; F 15: 2; S 16: 2; M 18: 2; T 19: 2
1 | 00609926 | VALTERRA | 82882-C | THERMOKING | 50 | 2000 | Prepration - Cutting Laser Module |  |  | 1200 | F 1: 240; S 2: 240; M 4: 240; T 5: 240; W 6: 240
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 1280 | F 1: 240; S 2: 240; M 4: 240; T 5: 240; W 6: 240; T 7: 80
2 | 00609945 | VALTERRA | 82882-C | THERMOKING | 50 | 1000 | Prepration - Cutting Laser Module |  |  | 1000 | T 7: 240; F 8: 240; S 9: 240; M 11: 240; T 12: 40
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 1000 | T 7: 140; F 8: 240; S 9: 240; M 11: 240; T 12: 140
3 | 00609914 | VALTERRA | 0 | THERMOKING | 110 | 1500 | Prepration - Cutting Laser Module |  |  | 1500 | T 12: 160; W 13: 240; T 14: 240; F 15: 240; S 16: 240; M 18: 240; T 19: 140
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 1500 | T 12: 80; W 13: 240; T 14: 240; F 15: 240; S 16: 240; M 18: 240; T 19: 220
[7 empty] | Prepration - Cutting Laser Module |  |  | 3700
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 3780
Preparation - Laminating = 1 Shift
Cutting Module - Packing = 2 Shift
DONE
DONE
DONE
DONE
J-BOX - Packing = 2 Shift
Arrival J-Box Material
DONE
Pick Up, 14 Mar
Pick Up, 16 Mar (20:00)
Pick Up, 16 Mar (20:00)
Pick Up, 30 Mar
DONE
Pick Up, 27 Mar
Note on U8: Yutio Sapnanda: WIP w/o J-Box
Note on X8: Yutio Sapnanda: Incoming Check, Instalation J-Box & Packing Box
Note on Y8: Yutio Sapnanda: Shift 1 Finish
Note on Y10: Yutio Sapnanda: Shift 2
Note on AE29: Yutio Sapnanda: ETA Port JKT 16 Mar (Sveck) ETA SKY, 17 Mar (Afternoon)
Note on AL29: Yutio Sapnanda: ETA 18 Mar (Boujun)
Note on AP29: "Al Isra Wal Miraj Prophet Mohammad SAW's Miraculous Journey".
Note on AR29: Chinese New Year

## Man Power
| MONITORING PLANNING | [16 empty] | Calculation Cost
| LABOR COST |  | FEBRUARY 2026 | [8 empty] | Apendix 3 | [5 empty] | Direct Labor |  | Valterra Project
Shift 1 | Direct Labor |  |  | Qty | Total | Shift 2 | Direct Labor |  |  |  |  | Qty | Total |  |  | No | Month | Working Day |  |  |  | Man Power | Cost
| Station |  | Process |  |  |  | Station |  |  | Process | [7 empty] | Days |  | Shift | Qty |  | / Day | Month
| ▪ | Preparation | Sortr Cell & Cutting Cell | 2 | 25 |  | ▪ | Preparation |  | Sortr Cell & Cutting Cell |  | 2 | 25 |  |  | 1 | March | a. | Normal Days | 2 | 15 | 80 | 18660599 | 279908985
|  |  | Cutting Eva & Backsheet | 2 | [5 empty] | Cutting Eva & Backsheet |  | 2 | [5 empty] | b. | Saturday | 2 | 3 | 80 | 19271203.4 | 57813610.2
|  |  | Cutting Ribbon & Busbar | 1 | [5 empty] | Cutting Ribbon & Busbar |  | 1 | [7 empty] | Total : | 18 |  |  | 337722595.2
|  |  | Assembling Junction Box | 2 | [5 empty] | Assembling Junction Box |  | 2 |  |  |  | 2. | April | a. | Normal Days | 2 | 20 | 80 | 18660599 | 373211980
| ▪ | Soldering | Series Soldering | 5 |  |  | ▪ | Soldering |  | Series Soldering |  | 5 | [5 empty] | b. | Saturday | 2 | 3 | 80 | 19271203.4 | 57813610.2
|  |  | Lay - Up (Assymbling Module) | 6 | [5 empty] | Lay - Up (Assymbling Module) |  | 6 | [7 empty] | Total : | 23 |  |  | 431025590.2
| ▪ | Inspection Quality | EL - Test | 1 |  |  | ▪ | Inspection Quality |  | EL - Test |  | 1 |  |  |  | 3. | May | a. | Normal Days | 2 | 15 | 80 | 18660599 | 279908985
|  |  | Visual Check | 2 | [5 empty] | Visual Check |  | 2 | [5 empty] | b. | Saturday | 2 | 3 | 80 | 19271203.4 | 57813610.2
| ▪ | Laminating | Laminated Process | 2 |  |  | ▪ | Laminating |  | Laminated Process |  | 2 | [7 empty] | Total : | 18 |  |  | 337722595.2
|  |  | Application Protection Film | [6 empty] | Application Protection Film | [9 empty] | Grand Total : | 59 |  |  | 1106470780.6
| ▪ | Assymbling | Cutting Module & Instalasi Grommet | 2 |  |  | ▪ | Assymbling |  | Cutting Module & Instalasi Grommet |  | 2
|  | Additional Man Power | [5 empty] | Additional Man Power
Non Shift | Direct Labor |  |  | Qty | Total | Shift 1 & 2 | Direct Labor |  |  |  |  | Qty | Total |  |  | No | Working Day |  |  |  |  | Man Power | Cost
| Station |  | Process |  |  |  | Station |  |  | Process | [6 empty] | Days |  |  | Shift | Qty |  | / Day | Month
| ▪ | Assymbling | Instalasi Junction Box | 2 | 16 |  | ▪ | Production |  | Leader Production (Permanent) |  | 4 | 14 |  |  | 1 | Monday - Friday |  |  | 2 | 1 | 80 | 1166.2874 | 1166.2874
| ▪ | Inspection Quality | Test IV (Sunsimulator) | 1 | [5 empty] | Raw Material (Daily) |  | 1 |  |  |  | 2 | Saturday |  |  | 2 | 1 | 80 | 1204.4502 | 1204.4502
|  |  | EL - Test | 1 | [5 empty] | Officer Production (Daily) |  | 1 | [7 empty] | Grand Total : | 2 |  |  | 2370.7377
| ▪ | Coating Process | Application Potting gell | 2 |  |  | ▪ | Quality Control |  | Quality Process Shift 1 (Daily) |  | 1 | [11 empty] | 0.14817
| ▪ | Finishing Process | Cleaning,Last Inspection, Labeling & Application Buble Wrap | 8 | [5 empty] | Quality Process Shift 2 (Daily) |  | 1
| ▪ | Packing Process | Packing Product | 2 | [5 empty] | Officer Quality Control (Daily) |  | 1
|  | Additional Man Power |  |  |  |  | ▪ | Maintenance |  | Maintenace Shift 1 (Daily) |  | 1
[10 empty] | Maintenance Shift 2 (Daily) |  | 1
[7 empty] | ▪ | Engineering |  | Engineering Field (Daily) |  | 1
[10 empty] | Officer Engineering (Daily) |  | 1
[7 empty] | ▪ | PPIC |  | Officer PPIC (Daily) |  | 1
Additional Man Power
Total | Direct Labor |  |  | Qty | Total | ▪ Calculation Cost
| Station |  | Process
| ▪ | Leader | Permanent Employed | 4 | 80 | 1. Man Power |  |  | : | 73 | 232573 | 16977829 |  |  | 2000000 |  | 146000000 |  | 13.7617 | 288.996
| ▪ | Raw Material | Daily Employed | 1 |  | 2. Leader QC & MTC |  |  | : | 2 | 239110 | 478220 |  |  | 4350000 |  | 8700000
| ▪ | Officer | Daily Employed | 4 |  | 3. Officer Engineering (Daily) |  |  | : | 1 | 248110 | 248110 |  |  | 4350000 |  | 4350000
| ▪ | Maintenance | Daily Employed | 2 |  | 4. Permanent Employed |  |  | : | 4 | 239110 | 956440 |  | + | 4350000 |  | 17400000 |  |  |  |  | +
| ▪ | Quality | Daily Employed | 2 | [7 empty] | 18660599 |  |  |  |  | 176450000 |  |  | 195936289.5
| ▪ | Engineering | Daily Employed | 1 |  | ▪ Cost for Overtime (Saturday) | [13 empty] | 12246.0181
| ▪ | Man Power | Daily Employed | 66 |  | 1. Permanent Employed |  |  | : | 4 | 152651.1 | 610604.4
|  | Additional Man Power | [11 empty] | +
610604.4
930292
[8 empty] | Upah Harian (8 Jam) |  | Tunjangan Sif | Uang Makan | Total |  | HK
[8 empty] | 218073 |  | 1000 | 13500 | 232573 |  | 4 | 930292

## Schedule Production (4) (hidden)
|  | February 2026 | [5 empty] | Updated : | 2026-03-10
MASTER PLANNING SCHEDULE
|  |  | Idle : | 7 |  | Normal Days : | 20 | Working Days : | 13 |  | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
No | No PO | Customers | Detailed Product |  |  | Qty (Order) | Production Process |  |  | Total Plan | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
|  |  | Type | Label | Wp | [5 empty] | M 9: 2; T 10: 2; W 11: 2; T 12: 2; F 13: 2; S 14: 2; M 16: 2; T 17: 2; W 18: 2; T 19: 2; F 20: 1; T 26: 2; F 27: 2; S 28: 2
1 | 00609804 (No.6) | VALTERRA | 73907-F | THERMOKING | 35 | 1000 | Prepration - Cutting Laser Module |  |  | 450 | F 6: 150; M 9: 160; T 10: 140
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 460 | M 9: 240; T 10: 220
2 | 00609684 (No.5) | VALTERRA | 82882-C | NAVIGATOR | 50 | 1000 | Prepration - Cutting Laser Module |  |  | 1000 | T 10: 80; W 11: 240; T 12: 240; F 13: 240; S 14: 200
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 960 | T 10: 60; W 11: 240; T 12: 240; F 13: 240; S 14: 180
4 | 00609820 (Part 1) (No.8) | VALTERRA | 73907-F | THERMOKING | 35 | 500 | Prepration - Cutting Laser Module |  |  | 500 | W 18: 180; T 19: 240; F 20: 80
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 320 | W 18: 60; T 19: 140; F 20: 120
5. | 00609820 (Part 2) (No.8) | VALTERRA | 73907-F | THERMOKING | 35 | 1500 | Prepration - Cutting Laser Module |  |  | 0 | bar: S 15 to T 17
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 0 | bar: S 15 to T 17
5 | 00609880 | VALTERRA | 82882-C | THERMOKING | 50 | 1000 | Prepration - Cutting Laser Module |  |  | 0
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 0
[7 empty] | Prepration - Cutting Laser Module |  |  | 1950 | T 12: 35W (PO.9804); M 16: 50W (PO.9684); F 20: 35W (PO.9804 & 9820); W 25: 35W (PO.9820)
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 1740 | F 13: 450 PCS (US); T 17: 540 pcs (IRE); F 20: 10 + 320 PCS (US); T 26: 180 PCS; S 28: (US)
50W (PO.9684)
|  | March 2026 | [8 empty] | S 21: 420 pcs; M 23: (IRE)
MASTER PLANNING SCHEDULE
|  |  | Idle : | 0 |  | Normal Days : | 19 | Working Days : | 19 |  | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T
No | No PO | Customers | Detailed Product |  |  | Qty (Order) | Production Process |  |  | Total Plan | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
|  |  | Type | Label | Wp | [9 empty] | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | [7 empty] | 2 | 2 | 2 | 2 |  | 2 | 2
1 | 00609684 (No.5) | VALTERRA | 82882-C | NAVIGATOR | 50 | 1000 | Prepration - Cutting Laser Module |  |  | 0 | bar: W 18 to T 24
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 40 | T 5: 40
2 | 00609820 (Part 1) (No.8) | VALTERRA | 73907-F | THERMOKING | 35 | 500 | Prepration - Cutting Laser Module |  |  | 0 | bar: W 18 to T 24
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 180 | T 5: 180
3 | 00609820 (Part 2) (No.8) | VALTERRA | 73907-F | THERMOKING | 35 | 1500 | Prepration - Cutting Laser Module |  |  | 1500 | F 6: 160; S 7: 220; S 8: 280; M 9: 280; T 10: 80; W 11: 280; T 12: 200
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 1500 | F 6: 80; S 7: 140; S 8: 240; M 9: 80; S 14: 600; S 15: 300; M 16: 60
4 | 00609784 (No.7) | VALTERRA | 82882-C | NAVIGATOR | 50 | 1000 | Prepration - Cutting Laser Module |  |  | 1000 | T 10: 140; F 13: 240; S 14: 120; W 25: 120; T 26: 180; F 27: 200
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 1000 | T 10: 140; S 15: 360; W 25: 80; T 26: 180; F 27: 240
5 | 00609820 (Part 3) (No.8) | VALTERRA | 73907 - F | THERMOKING | 35 | 2000 | Prepration - Cutting Laser Module |  |  | 840 | S 28: 280; M 30: 280; T 31: 280
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 840 | S 28: 280; M 30: 280; T 31: 280
[7 empty] | Prepration - Cutting Laser Module |  |  | 2500 | S 7: 35W (PO.9820); T 10: 35W (PO.9820); F 13: 50W (PO.9684 & 9784); T 17: 35W PO.9820; F 27: 35W (PO.9820); M 30: 35W (PO.9820)
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 2720 | S 7: 180 pcs; T 10: 540 PCS; F 13: 40 + 140 PCS; T 17: 900 pcs; F 27: 540; M 30: 920
50W PO.9784
|  | April 2026 | [7 empty] | 2000 | T 17: 360 pcs
|  | MASTER PLANNING SCHEDULE | [7 empty] | 2000
|  |  | Idle : | -4 |  | Normal Days : | 19 | Working Days : | 23 |  | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T
No | No PO | Customers | Detailed Product |  |  | Qty (Order) | Production Process |  |  | Total Plan | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
|  |  | Type | Label | Wp | [5 empty] | 2 | 2 |  |  |  |  | 2 | 2 | 2 | 2 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 |  | 2 | 2 | 2 | 2
1 | 00609784 (No.7) | VALTERRA | 82882-C | NAVIGATOR | 50 | 1000 | Prepration - Cutting Laser Module |  |  | 1160 | W 1: 280; T 2: 280; T 7: 280; W 8: 280; T 9: 40
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 1160 | W 1: 280; T 2: 280; T 7: 280; W 8: 280; T 9: 40
3 | 00609880 (No.9) | VALTERRA | 82882-C | THERMOKING | 50 | 1000 | Prepration - Cutting Laser Module |  |  | 1000 | T 9: 200; F 10: 240; S 11: 240; M 13: 240; T 14: 80
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 1000 | T 9: 200; F 10: 240; S 11: 240; M 13: 240; T 14: 80
4 | 00609900 | VALTERRA | 73907 - F | THERMOKING | 50 | 1000 | Prepration - Cutting Laser Module |  |  | 1000 | M 13: 160; T 14: 240; W 15: 240; T 16: 240; F 17: 120
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 1000 | T 14: 180; W 15: 240; T 16: 240; F 17: 240; S 18: 100
5 | 00609915 | VALTERRA | 82882-C | THERMOKING | 35 | 2000 | Prepration - Cutting Laser Module |  |  | 2000 | F 17: 120; S 18: 280; M 20: 280; T 21: 280; W 22: 280; T 23: 280; F 24: 280; S 25: 200
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 2000 | S 18: 120; M 20: 280; T 21: 280; W 22: 280; T 23: 280; F 24: 280; S 25: 280; M 27: 200
6 | 00609926 | VALTERRA | 82882-C | THERMOKING | 50 | 2000 | Prepration - Cutting Laser Module |  |  | 1040 | M 27: 200; T 28: 280; W 29: 280; T 30: 280
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 920 | M 27: 80; T 28: 280; W 29: 280; T 30: 280
[7 empty] | Prepration - Cutting Laser Module |  |  | 5160
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 5160
May 2026
MASTER PLANNING SCHEDULE
|  |  | Idle : | 3 |  | Normal Days : | 19 | Working Days : | 16 |  | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
No | No PO | Customers | Detailed Product |  |  | Qty (Order) | Production Process |  |  | Total Plan | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
|  |  | Type | Label | Wp | [5 empty] | F 1: 2; S 2: 2; M 4: 2; T 5: 2; W 6: 2; T 7: 2; F 8: 2; S 9: 2; M 11: 2; T 12: 2; W 13: 2; T 14: 2; F 15: 2; S 16: 2; M 18: 2; T 19: 2
1 | 00609926 | VALTERRA | 82882-C | THERMOKING | 50 | 2000 | Prepration - Cutting Laser Module |  |  | 960 | F 1: 240; S 2: 240; M 4: 240; T 5: 240
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 1080 | F 1: 240; S 2: 240; M 4: 240; T 5: 240; W 6: 120
2 | 00609945 | VALTERRA | 82882-C | THERMOKING | 50 | 1000 | Prepration - Cutting Laser Module |  |  | 1000 | W 6: 240; T 7: 240; F 8: 240; S 9: 240; M 11: 40
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 1000 | W 6: 80; T 7: 240; F 8: 240; S 9: 240; M 11: 200
3 | 00609914 | VALTERRA | 0 | THERMOKING | 110 | 1500 | Prepration - Cutting Laser Module |  |  | 1500 | M 11: 160; T 12: 240; W 13: 240; T 14: 240; F 15: 240; S 16: 240; M 18: 140
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 1500 | T 12: 240; W 13: 240; T 14: 240; F 15: 240; S 16: 240; M 18: 240; T 19: 60
[7 empty] | Prepration - Cutting Laser Module |  |  | 3460
[7 empty] | Instalation Junction Box - Packaging Process |  |  | 3580
Estimated Arrival J-Box Material
DONE
DONE
DONE
DONE
DONE
Pick Up, 14 Mar
Pick Up, 11 Mar
Pick Up, 16 Mar (21:00)
Pick Up, 16 Mar (21:00)
Note on U8: Yutio Sapnanda: WIP w/o J-Box
Note on X8: Yutio Sapnanda: Incoming Check, Instalation J-Box & Packing Box
Note on Y8: Yutio Sapnanda: Shift 1 Finish
Note on Y10: Yutio Sapnanda: Shift 2
Note on AP29: "Al Isra Wal Miraj Prophet Mohammad SAW's Miraculous Journey".
Note on AR29: Chinese New Year

## Planning Man Power (hidden)
MONITORING PLANNING
| MAN POWER |  |  | 26 - 28 FEBRUARY 2026
Shift 1 | Direct Labor |  |  |  | Qty | Total | Man Power Name | [7 empty] | Total | Prepared by,
| Station |  | Process |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
| ▪ | Preparation | Sortr Cell & Cutting Cell |  | 2 | 25 | [8 empty] | 0
|  |  | Cutting Eva & Backsheet |  | 2 | [9 empty] | 0
|  |  | Cutting Ribbon & Busbar |  | 1 | [9 empty] | 0
|  |  | Assembling Junction Box |  | 2 | [9 empty] | 0
| ▪ | Soldering | Series Soldering |  | 5 | [9 empty] | 0
|  |  | Lay - Up (Assymbling Module) |  | 6 | [9 empty] | 0
| ▪ | Inspection Quality | EL - Test |  | 1 | [9 empty] | 0
|  |  | Visual Check |  | 2 | [9 empty] | 0
| ▪ | Laminating | Laminated Process |  | 2 | [9 empty] | 0
|  |  | Application Protection Film | [11 empty] | 0
| ▪ | Assymbling | Cutting Module & Instalasi Grommet |  | 2 | [9 empty] | 0 | Checking by,
|  | Additional Man Power | [12 empty] | 0
Non Shift | Direct Labor |  |  |  | Qty | Total | Man Power Name 1: Man Power Name | Total
| Station |  | Process |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
| ▪ | Assymbling | Instalasi Junction Box |  | 2 | 16 | [8 empty] | 0
| ▪ | Inspection Quality | Test IV (Sunsimulator) |  | 1 | [9 empty] | 0
|  |  | EL - Test |  | 1 | [9 empty] | 0
| ▪ | Coating Process | Application Potting gell |  | 2 | [9 empty] | 0
| ▪ | Finishing Process | Cleaning,Last Inspection, Labeling & Application Buble Wrap |  | 8 | [9 empty] | 0
| ▪ | Packing Process | Packing Product |  | 2 | [9 empty] | 0
|  | Additional Man Power | [12 empty] | 0
Approved by
Shift 2 | Direct Labor |  |  |  | Qty | Total | Man Power Name 1: Man Power Name | Total
| Station |  | Process |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
| ▪ | Preparation | Sortr Cell & Cutting Cell |  | 2 | 25 | [8 empty] | 0
|  |  | Cutting Eva & Backsheet |  | 2 | [9 empty] | 0
|  |  | Cutting Ribbon & Busbar |  | 1 | [9 empty] | 0
|  |  | Assembling Junction Box |  | 2 | [9 empty] | 0
| ▪ | Soldering | Series Soldering |  | 5 | [9 empty] | 0
|  |  | Lay - Up (Assymbling Module) |  | 6 | [9 empty] | 0
| ▪ | Inspection Quality | EL - Test |  | 1 | [9 empty] | 0
|  |  | Visual Check |  | 2 | [9 empty] | 0
| ▪ | Laminating | Laminated Process |  | 2 | [9 empty] | 0
|  |  | Application Protection Film | [11 empty] | 0 | Approved by
| ▪ | Assymbling | Cutting Module & Instalasi Grommet |  | 2 | [9 empty] | 0
|  | Additional Man Power | [12 empty] | 0
Shift 1 & 2 | Direct Labor |  |  |  | Qty | Total | Man Power Name 1: Man Power Name | Total
| Station |  |  | Process |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
| ▪ | Production | Leader Production (Permanent) |  | 3 | 14 | Man Power Name 1: Aulia; Man Power Name 2: Resti; Man Power Name 3: Dede | 3
|  |  | Raw Material (Permanent) |  | 1 |  | Man Power Name 1: Mulyadi | 1
|  |  | Raw Material (Daily) |  | 1 |  | Man Power Name 1: Felix | 1
|  |  | Officer Production (Daily) |  | 1 |  | Man Power Name 1: Ayu N | 1
| ▪ | Quality Control | Quality Process Shift 1 (Daily) |  | 1 |  | Man Power Name 1: Tika | 1
|  |  | Quality Process Shift 2 (Daily) |  | 1 |  | Man Power Name 1: Roura | 1
|  |  | Officer Quality Control (Daily) |  | 1 |  | Man Power Name 1: Tita | 1
| ▪ | Maintenance | Maintenace Shift 1 (Daily) |  | 1 |  | Man Power Name 1: Sandi | 1
|  |  | Maintenance Shift 2 (Daily) |  | 1 |  | Man Power Name 1: Ali | 1
| ▪ | Engineering | Engineering Field (Daily) |  | 1 |  | Man Power Name 1: Hairul R | 1
|  |  | Officer Engineering (Daily) |  | 1 |  | Man Power Name 1: Yulianti P | 1
| ▪ | PPIC | Officer PPIC (Daily) |  | 1 |  | Man Power Name 1: Dhean A | 1
|  | Additional Man Power | [12 empty] | 0
[5 empty] | Total Plan Man Power : | 80 | Man Power Name 8: Total Man Power : | 14